NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM

Project Execution Plan · Technical Specification · Feature Catalogue

Project Title: Nifty 100 Financial Intelligence Platform

Document Type: Full Technical Specification & Project Execution Plan

Duration: 45 Calendar Days | 6 Weekly Sprints | 3 Buffer Days

Dataset Universe: 92 Nifty 100 Companies | 7 Core + 5 Supplementary Datasets Total Records: ~11,000+ Data Points Across All Financial Statements

Platform: 12 Modules | 120+ Features | 50+ Financial KPIs

Document Pages: 50 Pages

CONFIDENTIAL · INTERNAL USE ONLY · DATA ANALYTICS DIVISION Version 1.0 · June 2026

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

1. Document Control & Classification Administrative Record

| Field | Detail |
| --- | --- |
| Document Title | Nifty 100 Financial Intelligence Platform — Project Execution Plan |
| Document ID | DAD-PROJ-001 ¦ Version 1.0 |
| Classification | Confidential — Internal Use Only |
| Status | Approved for Distribution |
| Project Duration | 45 Calendar Days ¦ 6 Weekly Sprints ¦ 3 Buffer Days |
| Effective Date | June 2026 |
| Owner | Data Analytics Division — Project Lead |
| Distribution | Data Analyst Team Members (individually assigned) |
| Total Pages | 50 |
| Datasets | 7 Core Datasets + 5 Supplementary Datasets |
| Companies | 92 (Nifty 100 Index Constituents) |
| KPIs Defined | 50+ Financial Key Performance Indicators |
| Currency Standard | All monetary values in Indian Rupees — Crore (■ Cr) unless stated |

Version History

| Version | Date | Change Description |
| --- | --- | --- |
| 1.0 | June 2026 | Initial release — full specification for 45-day project |
| 1.1 | Post-Sprint 1 | Updates based on data quality findings from ETL validation |
| 1.2 | Post-Sprint 3 | Screener and scoring refinements after testing |
| 2.0 | Day 45 | Final delivery version — all acceptance criteria verified |

How to Use This Document

| Section | Pages | Primary Reader | Purpose |
| --- | --- | --- | --- |
| 1 — Document Control | 2 | All | Classification, version history, reader guide |
| 2 — Table of Contents | 3 | All | Navigation index |
| 3 — Executive Summary | 4–5 | All | Platform overview, key metrics, outcomes |
| 4 — Project Overview | 6–7 | All | Objectives, scope, stakeholder RACI |
| 5 — Dataset Catalogue | 8–14 | Data Engineers | Full data dictionary for all 12 datasets |
| 6 — Data Relationships | 15 | All | Entity relationships, join patterns, data gaps |
| 7 — System Architecture | 16 | All | Folder structure, layers, data flow |
| 8–19 — Module Specifications 17–34 |  | Analysts | Feature-by-feature breakdown of all 12 modules |
| 20 — Sprint Plan & Timeline | 35–40 | All | Day-by-day tasks, exit criteria for each sprint |
| 21 — KPI Reference | 41–43 | Analytics | Formulas, edge cases, benchmarks for 50+ KPIs |
| 22 — Data Quality Rules | 44 | Data Engineers | 14 validation rules — severity, action, test |
| 23 — API Specification | 45 | Backend | Optional FastAPI endpoint definitions |
| 24 — Risk Register | 46 | Project Lead | Risks, likelihood, impact, mitigations |
| 25 — Deliverables Checklist | 47 | All | What to submit, format, due date, evaluation |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 2

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

| Section | Pages | Primary Reader | Purpose |
| --- | --- | --- | --- |
| 26 — Tech Stack & Standards 48 |  | All | Libraries, versions, code quality gates |
| 27 — Acceptance Criteria | 49 | All | 20 mandatory gates — definition of done |
| 28 — Glossary | 50 | All | Definitions of all technical terms |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 3

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

Table of Contents

Section Title Pg

1 Document Control & Classification 2 2 Table of Contents 3 3 Executive Summary 4 4 Project Overview & Objectives 6 4.1 Mission & Objectives Matrix 6 4.2 Scope Boundaries 6 4.3 Stakeholder Matrix & RACI 7 5 Dataset Catalogue — Core Datasets 8 5.1 companies.xlsx 8 5.2 profitandloss.xlsx 9 5.3 balancesheet.xlsx 10 5.4 cashflow.xlsx 11 5.5 analysis.xlsx 11 5.6 documents.xlsx 12 5.7 prosandcons.xlsx 12 6 Supplementary Datasets 13 6.1–6.5 sectors / stock_prices / market_cap / financial_ratios / peer_groups 13 7 Data Relationships & Entity Map 15 8 System Architecture 16 9 Module 1 — Data Engineering & ETL Pipeline 17 10 Module 2 — Financial Ratio Engine (50+ KPIs) 19 11 Module 3 — Company Intelligence Dashboard 22 12 Module 4 — Investment Screener 23 13 Module 5 — Financial Health Scoring Model 25 14 Module 6 — Sector Analytics 27 15 Module 7 — Cash Flow Intelligence 29 16 Module 8 — Trend & Growth Analytics 30 17 Module 9 — Peer Comparison Engine 31 18 Module 10 — Reporting & Export Engine 32 19 Module 11 — Document Intelligence Repository 33 20 Module 12 — Alerts & Watchlist 34 21 45-Day Sprint Plan & Timeline 35 21.1 Sprint 1 — Foundation & Data Engineering 35 21.2 Sprint 2 — Financial Ratio Engine 36 21.3 Sprint 3 — Screener, Scoring & Sector Analytics 37 21.4 Sprint 4 — Peer, Trend, Cash Flow & Documents 38 21.5 Sprint 5 — Dashboard & Reporting 39 21.6 Sprint 6 — Testing, Documentation & Delivery 40 22 KPI Definitions & Business Logic 41 23 Data Quality & Validation Rules 44 24 API & Service Layer Specification 45 25 Risk Register 46

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 4

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

26 Deliverables Checklist 47 27 Technical Stack & Code Standards 48 28 Acceptance Criteria — Definition of Done 49 29 Glossary of Terms 50

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 5

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

3. Executive Summary Strategic Overview & Key Metrics

| Attribute | Detail |
| --- | --- |
| Platform Name | Nifty 100 Financial Intelligence Platform |
| Core Purpose | Transform raw financial statement data into structured analytics intelligence for 92 Nifty 100 companies |
| Data Foundation | 7 core + 5 supplementary datasets covering P&L, Balance Sheet, Cash Flow, Sectors, Market Cap, Pricing |
| Analytical Scope | 10–13 years of annual financial history per company; 50+ computed KPIs; 12 analytics modules |
| Primary Outputs | Investment screener, financial health scores, sector benchmarks, automated PDF/Excel reports, Streamlit dashboard |
| Target Users | Data Analysts — individually assigned to specific modules per this project document |
| Build Timeline | 45 calendar days ¦ 6 weekly sprints ¦ 3 buffer days |
| Quality Standard | Production-grade: ≥80% test coverage, full documentation, zero critical bugs at handoff |
| Currency Standard | All monetary values in Indian Rupees — Crore (■ Cr) unless explicitly stated otherwise |
| Index Universe | Nifty 100 — 92 companies after data availability filter applied |

| Category | Metric | Value | Category | Metric | Value |
| --- | --- | --- | --- | --- | --- |
| Data | Core Datasets | 7 | Platform | Analytics Modules | 12 |
| Data | Supplementary Datasets | 5 | Platform | Total Features | 120+ |
| Data | Total Companies | 92 | Platform | Financial KPIs | 50+ |
| Data | P&L Records | 1,276 | Platform | Screener Filters | 18 |
| Data | Balance Sheet Records | 1,312 | Platform | Pre-built Screens | 6 |
| Data | Cash Flow Records | 1,187 | Platform | Peer Groups | 11 |
| Data | Annual Report Links | 1,585 | Platform | Sector Categories | 11 |
| Data | Stock Price Records | 5,520 | Quality | Test Coverage Target | ≥80% |
| Data | Computed Ratio Records | 1,184 | Quality | DQ Validation Rules | 14 |
| Time | Total Duration | 45 Days | Quality | Acceptance Criteria | 20 |

| # | Key Outcome | Business Value | Owner Module |
| --- | --- | --- | --- |
| 01 |  | Unified financial data warehouse for 92 companies Single source of truth; eliminates manual data gathering ETL Pipeline |  |
| 02 |  | 50+ computed KPIs per company per year Instant quantitative assessment without manual calculation Ratio Engine |  |
| 03 |  | Multi-parameter investment screener (18 filters) Reduces analyst time-to-insight from hours to seconds Screener |  |
| 04 |  | Composite Financial Health Score (0–100) Standardised risk triage across the full universe Health Score |  |
| 05 |  | Sector benchmarks across 11 broad sectors Sector rotation analysis and relative positioning Sector Analytics |  |
| 06 |  | Peer comparison engine for 11 peer groups Identifies best-in-class within comparable peer universes Peer Comparison |  |
| 07 |  | Automated PDF and Excel report generation Reproducible, consistent output; eliminates manual writing Reporting |  |
| 08 |  | Streamlit dashboard — analyst-facing interface Zero-code interface for non-programmer stakeholders Dashboard |  |
| 09 |  | Annual report repository — 1,585 links Direct access to primary source documents Document Repo |  |
| 10 |  | Rule-based alert system and company watchlist Proactive KPI deterioration monitoring | Alerts |

| Sprint | Days | Focus Area | Primary Deliverable | Exit Gate |
| --- | --- | --- | --- | --- |
| Sprint 1 | 1–7 | Foundation & ETL | SQLite DB loaded; DQ report | 0 critical DQ violations; ≥80% ETL coverage |
| Sprint 2 | 8–14 | Ratio Engine | 50+ KPIs in financial_ratios table | Values validated vs 5 companies ±2% |
| Sprint 3 | 15–21 | Screener, Score & Sector | Screener, FHS, Sector module | All 3 modules correct; scores 0–100 for all 92 |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 6

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

| Sprint | Days | Focus Area | Primary Deliverable | Exit Gate |
| --- | --- | --- | --- | --- |
| Sprint 4 | 22–28 | Peer / Trend / CF / Docs | 4 analytics modules complete | All modules integrated; peer comparison works |
| Sprint 5 | 29–35 | Dashboard & Reporting |  | Streamlit app; PDF/Excel generatorsApp runs; 10+ company PDFs generated |
| Sprint 6 | 36–45 | Testing, Docs & Delivery | v1.0 tagged release | ≥80% coverage; 0 critical bugs; README verified |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 7

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

4. Project Overview & Objectives 4.1 Mission & Objectives Matrix

Mission, Scope, Stakeholders & Governance

| Attribute | Statement |
| --- | --- |
| Mission | Build a self-contained, production-grade financial intelligence system enabling analysts to query, screen, score, and compare all 92 N |
| Vision | Become the definitive internal reference for Nifty 100 fundamental analysis — reproducible, auditable, and version-controlled from pu |
| Principle | Every insight must be traceable to a formula, every formula to a source column, every column to a dataset file. No black-box number |

| ID | Objective | Success Metric | Priority | Sprint |
| --- | --- | --- | --- | --- |
| O-01 | Data Engineering | All 12 datasets loaded; 0 critical DQ violations Critical |  | 1 |
| O-02 | KPI Computation | 50+ KPIs for all company-year combinations Critical |  | 2 |
| O-03 | Investment Screener | 18 filter types; 6 pre-built templates return results Critical |  | 3 |
| O-04 | Financial Health Scoring | 0–100 score for all 92 companies; correct bands Critical |  | 3 |
| O-05 | Sector Analytics | Median KPIs for all 11 sectors; sector ranking High |  | 3 |
| O-06 | Peer Comparison | Percentile ranks for all 11 peer groups | High | 4 |
| O-07 | Trend & Growth Analytics | 1Y/3Y/5Y/10Y CAGR for revenue, profit, EPS High |  | 4 |
| O-08 | Cash Flow Intelligence | Capital allocation matrix for all 92 companies High |  | 4 |
| O-09 | Dashboard | Streamlit app — 5 pages functional; no crash High |  | 5 |
| O-10 | PDF Report Generation | Company + sector PDFs for all 92 + 11 sectors High |  | 5 |
| O-11 | Excel Exports | Screener export, full universe, comparison exports Medium |  | 5 |
| O-12 | Alerts & Watchlist | Threshold alerts; YoY deterioration detection Medium |  | 6 |
| O-13 | Test Coverage | ≥80% unit test coverage across src/ | Critical | 6 |
| O-14 | Documentation | README: fresh setup in <30 min; docstrings on all functions High 6 |  |  |

4.2 Scope Boundaries

| # | In Scope | # | Out of Scope |
| --- | --- | --- | --- |
| S01 | Fundamental analysis — P&L, Balance Sheet, Cash Flow X01 Real-time price feeds or live market data |  |  |
| S02 | Historical trend analysis — 10–13 years per companyX02 |  | Technical analysis (RSI, MACD, Bollinger Bands) |
| S03 | 50+ financial KPI computation from raw data | X03 | Machine learning price prediction models |
| S04 | Investment screener with 18 configurable filters | X04 | Options, derivatives, or futures analytics |
| S05 | Financial Health Score (0–100) composite model | X05 | User authentication or multi-tenancy |
| S06 | Sector benchmarking across 11 sectors | X06 | Cloud deployment or CI/CD infrastructure |
| S07 | Peer comparison for 11 defined peer groups | X07 | Insider trading or shareholding pattern data |
| S08 | Automated PDF and Excel report generation | X08 | ESG scoring or sustainability metrics |
| S09 | Streamlit dashboard — analyst interface | X09 | International or cross-market comparison |
| S10 | Annual report repository — 1,585 links | X10 | Portfolio construction or optimisation models |
| S11 | Simulated stock price & market cap datasets | X11 | Earnings call transcripts or news sentiment |
| S12 | Rule-based alert system and watchlist | X12 | Regulatory filing alerts or SEBI announcements |

4.3 Stakeholder Matrix & RACI

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 8

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

| Stakeholder | Role | Module Ownership | Engagement |
| --- | --- | --- | --- |
| Data Analyst — ETL | Data Engineer | Module 1 (ETL Pipeline) | Daily — Sprints 1–2 |
| Data Analyst — Analytics | KPI Developer | Modules 2, 5, 6, 7, 8, 9 | Daily — Sprints 2–4 |
| Data Analyst — Frontend | Dashboard Builder | Module 3, 4 UI (Screener page) | Daily — Sprint 5 |
| Data Analyst — Reporting Report Developer |  | Module 10 (PDF/Excel) | Daily — Sprint 5 |
| Data Analyst — QA | Quality Assurance | Test suite, documentation | Daily — Sprint 6 |
| Project Lead | Coordinator | All modules — review & integration | Weekly review meetings |

| Module | ETL Analyst | Analytics Analyst | Frontend Analyst | Reporting Analyst | QA Analyst |
| --- | --- | --- | --- | --- | --- |
| ETL Pipeline | R/A | C | I | I | C |
| Financial Ratio Engine | C | R/A | I | I | C |
| Investment Screener | I | R/A | C | I | C |
| Health Scoring | I | R/A | C | I | C |
| Sector Analytics | I | R/A | C | I | C |
| Peer Comparison | I | R/A | C | I | C |
| Trend & Growth | I | R/A | C | I | C |
| Cash Flow Intelligence | I | R/A | C | I | C |
| Dashboard | I | C | R/A | C | C |
| PDF / Excel Reports | I | C | C | R/A | C |
| Alerts & Watchlist | I | R | C | I | A |
| Full Test Suite | C | C | C | C | R/A |
| Documentation | C | C | C | C | R |

R = Responsible | A = Accountable | C = Consulted | I = Informed

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 9

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

5. Dataset Catalogue — Core Datasets

Schema, Data Dictionary, Quality Notes & Usage

| Dataset | Sheet | Records | Cols | Time Coverage | Primary Key | Currency |
| --- | --- | --- | --- | --- | --- | --- |
| companies.xlsx | Companies | 92 | 12 | Current snapshot | id (NSE ticker) | N/A |
| profitandloss.xlsx | Profit & Loss | 1,276 | 15 | FY 2010–2024 | (company_id, year) | ■ Crore |
| balancesheet.xlsx | Balance Sheet | 1,312 | 13 | FY 2010–2024 | (company_id, year) | ■ Crore |
| cashflow.xlsx | Cash Flow | 1,187 | 7 | FY 2010–2024 | (company_id, year) | ■ Crore |
| analysis.xlsx | Analysis | 20 | 6 | Multi-period text | company_id | % strings |
| documents.xlsx | Documents | 1,585 | 4 |  | Calendar 2010–2024 (company_id, Year) | N/A — URLs |
| prosandcons.xlsx | Pros & Cons | 16 | 4 | Current | id (auto) | N/A — text |

Load note: Core files use pd.read_excel(path, header=1) — Row 0 is metadata; Row 1 is actual headers. Supplementary files use header=0. Normalise company_id to uppercase stripped NSE ticker on every load.

5.1 companies.xlsx — Master Company Reference

| Column | Type | Nullable | Sample Value | Description & Notes |
| --- | --- | --- | --- | --- |
| id | VARCHAR | No | TCS | NSE ticker — Primary Key for entire platform. Strip whitespace; uppercase. |
| company_logo | TEXT | Yes | https://…/TCS.png | URL to company logo image. Some may return 404 — handle gracefully. |
| company_name | VARCHAR | No |  | Tata Consultancy Services LtdFull legal name. Some entries contain embedded \n — strip on load. |
| chart_link | TEXT | Yes |  | https://in.tradingview.com/… TradingView chart URL. For display only; not used in computation. |
| about_company | TEXT | Yes | TCS is a leading IT… | Business description. Length: 50–600 chars. Display in company card. |
| website | TEXT | Yes | https://www.tcs.com/ | Official corporate website URL. |
| nse_profile | TEXT | Yes | https://nseindia.com/… | NSE India equity profile page URL. |
| bse_profile | TEXT | Yes | https://bseindia.com/… | BSE India stock page URL. |
| face_value | NUMERIC | No | 1 | Share face value in ■. Common: 1, 2, 5, 10. Used in book value calculation. |
| book_value | NUMERIC | Yes | 157.40 | Book value per share in ■ (latest). Display only; compute from BS for analytic |
| roce_percentage | NUMERIC | Yes | 64.30 | ROCE % (pre-computed). Use for display; Ratio Engine values for analytics. |
| roe_percentage | NUMERIC | Yes | 0.52 | ROE % (pre-computed). Note: TCS shows 0.52 — anomaly; use Ratio Engin |

5.2 profitandloss.xlsx — Annual Profit & Loss Statements

| Column | Type | Nullable | Sample (TCS FY23) | Formula / Notes |
| --- | --- | --- | --- | --- |
| id | INTEGER | No | 61 | Row ID — not analytically meaningful. Use composite key. |
| company_id | VARCHAR | No | TCS | FK → companies.id. Normalise to uppercase stripped ticker. |
| year | VARCHAR | No | Mar-23 | Financial year label. Standardise to 'YYYY-MM' on load via normalize_year(). |
| sales | NUMERIC | No | 225,458 | Net revenue / total income. Must be > 0. ■ Crore. |
| expenses | NUMERIC | No | 176,924 | Total operating expenses. ■ Crore. |
| operating_profit | NUMERIC | No | 48,534 | EBITDA. Cross-validate: must equal sales − expenses within ±1%. |
| opm_percentage | NUMERIC | No | 21.5 | OPM %. Validate: = operating_profit/sales×100 ±1%. Flag if diff >1%. |
| other_income | NUMERIC | Yes | 3,800 | Non-operating income (dividends received, interest). ■ |
| interest | NUMERIC | Yes | 0 | Finance costs. 0 for debt-free companies. ■ Crore. |
| depreciation | NUMERIC | Yes | 5,800 | D&A. ■ Crore. EBIT = operating_profit − depreciation. |

Crore.

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 10

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

| Column | Type | Nullable | Sample (TCS FY23) | Formula / Notes |
| --- | --- | --- | --- | --- |
| profit_before_tax | NUMERIC | Yes | 46,534 | PBT = EBITDA + other_income − interest − D&A. ■ Crore. |
| tax_percentage | NUMERIC | Yes | 25.0 | Effective tax rate %. Verify: (PBT − PAT) / PBT × 100. |
| net_profit | NUMERIC | Yes | 34,990 | PAT. Can be negative. ■ Crore. |
| eps | NUMERIC | Yes | 95.30 | Earnings Per Share in ■. Must be > 0 if net_profit > 0. |
| dividend_payout | NUMERIC | Yes | 45.0 | Dividend payout ratio %. Can exceed 100% in low-profit years. |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 11

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL 5.3 balancesheet.xlsx — Annual Balance Sheet

| Column | Type | Nullable | Sample (ABB 2024) | Formula / Notes |
| --- | --- | --- | --- | --- |
| id | INTEGER | No | 136 | Row ID. |
| company_id | VARCHAR | No | ABB | FK → companies.id. |
| year | VARCHAR | No | Mar-24 | Standardise to YYYY-MM. |
| equity_capital | NUMERIC | No | 21 | Paid-up share capital. Small for large caps. ■ Crore. |
| reserves | NUMERIC | Yes | 626 | Reserves & surplus. Total Equity = equity_capital + reserves. |
| borrowings | NUMERIC | Yes | 0 | Total debt (short + long term). 0 = debt-free. ■ Crore. |
| other_liabilities | NUMERIC | Yes | 260 | Trade payables + other current liabilities. Proxy for CL in ROCE. |
| total_liabilities | NUMERIC | No | 907 | Sum of equity + all liabilities. Must equal total_assets ±1%. |
| fixed_assets | NUMERIC | Yes | 109 | Net fixed assets (after D&A). ■ Crore. |
| cwip | NUMERIC | Yes | 1 | Capital Work In Progress. Add to fixed_assets for gross block proxy. |
| investments | NUMERIC | Yes | 0 | Long-term investments and securities. Used as liquid proxy for net debt. |
| other_asset | NUMERIC | Yes | 798 | Current assets + other assets. Catch-all non-fixed. |
| total_assets | NUMERIC | No | 907 | Sum of all asset-side items. Must equal total_liabilities ±tolerance. |

5.4 cashflow.xlsx — Annual Cash Flow Statements

| Column | Type | Sign Convention | Healthy Signal | Notes |
| --- | --- | --- | --- | --- |
| id | INTEGER | — | — | Row ID. |
| company_id | VARCHAR | — | — | FK → companies.id. |
| year | VARCHAR | — | — | Standardise to YYYY-MM. |
| operating_activity | NUMERIC | Positive = good | CFO > 0 consistently | Cash generated from core operations. Primary health indicator. |
| investing_activity | NUMERIC | Negative = normal |  | Negative = investing in growthCash used for CapEx, acquisitions, investments. |
| financing_activity | NUMERIC | Variable |  | Negative = debt repayment / dividends Debt raise/repay, equity issuance, dividends paid. |
| net_cash_flow | NUMERIC | Pos = cash grew | Positive preferred | = CFO + CFI + CFF. Validate: matches sum ±10 Crore. |

5.5 analysis.xlsx — Pre-Computed Growth Metrics (Partial Coverage)

| Column | Type | Sample Value | Parsing Logic | Usage |
| --- | --- | --- | --- | --- |
| id | INTEGER | 1 | Direct int cast | Row ID. |
| company_id | VARCHAR | HDFCBANK | Normalise ticker | FK → companies.id. |
| compounded_sales_growth | TEXT | 10 Years: 21% | Regex: r'(\d+)\s*Years?:?\s*([\d.]+)%' | →Display + cross-check after parsing (10, 21.0) |
| compounded_profit_growth | TEXT | 5 Years: 6% | Same pattern | Display + cross-check |
| stock_price_cagr | TEXT | 10 Years: 15% | Same pattern | Display only — compute from market_cap dataset |
| roe | TEXT | 10 Years: 17% | Same pattern | Display only — use Ratio Engine ROE for analytics |

■ Crore.

■ Cror

■ Crore.

■ Crore.

■ Crore.

Coverage gap: Only ~8 companies have entries. Compute growth metrics for all 92 via the Ratio Engine (Sprint 2). Use analysis.xlsx values only for display cross-check.

5.6 documents.xlsx — Annual Report Repository

| Column | Type | Nullable | Sample Value | Notes |
| --- | --- | --- | --- | --- |
| id | INTEGER | No | 1 | Row ID. |
| company_id | VARCHAR | No | ABB | FK → companies.id. |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 12

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

| Column | Type | Nullable | Sample Value | Notes |
| --- | --- | --- | --- | --- |
| Year | INTEGER | No | 2024 | Calendar year of annual report. Note: capital 'Y'. Cast to int. |
| Annual_Report | TEXT | Yes | https://bseindia.com/…pdf | Direct PDF URL on BSE India. Validate with requests.head(). Some return |

5.7 prosandcons.xlsx — Qualitative Investment Insights

| Column | Type | Nullable | Sample Value | Notes |
| --- | --- | --- | --- | --- |
| id | INTEGER | No | 1 | Row ID. |
| company_id | VARCHAR | No | HDFCBANK | FK → companies.id. |
| pros | TEXT | Yes |  | Company is expected to give good quarter Positive observation. One per row. Multiple rows per company allowed. |
| cons | TEXT | Yes | Stock trading at 2.76× book value Risk observation. One per row. |  |

Coverage gap: Only 16 records covering ~8 companies. Sprint 3 task: auto-generate pros/cons for all 92 companies using KPI threshold rules. Examples: ROE>20% sustained → pro; D/E>2.0 → con; FCF negative 3yr → con.

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 13

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

Created to Augment

Core Analysis —

6. Supplementary Datasets

Location: supporting

datasets/

| File | Rows | Created From | Analytical Purpose |
| --- | --- | --- | --- |
| sectors.xlsx | 92 |  | Manual GICS-style mapping of all 92 companies Sector/sub-sector aggregation, relative scoring, sector filter in scre |
| stock_prices.xlsx | 5,520 |  | Simulated monthly OHLCV — Jan 2020 to Dec 2024 Price trend charts, monthly return calculation, FCF yield denomina |
| market_cap.xlsx | 552 |  | Simulated annual P/E, P/B, EV/EBITDA, Mkt Cap Valuation screening (P/E, P/B), EV/EBITDA comp, dividend yield d |
| financial_ratios.xlsx | 1,184 |  | Computed from P&L + Balance Sheet + Cash Flow Pre-computed KPI table; screener backbone; health score inputs |
| peer_groups.xlsx | 56 |  | Manually defined 11 peer groups + benchmark flags Peer comparison engine; relative percentile ranking |

6.1 sectors.xlsx — Company Sector Mapping

| Column | Values / Range | Notes |
| --- | --- | --- |
| company_id | NSE Ticker (92 unique) | FK → companies.id. One row per company. |
| broad_sector | 11 macro sectors | Financials, Energy, IT, Consumer Discretionary, Consumer Staples, Healthcare, Materials, Industrials, Com |
| sub_sector | 33 sub-sectors | e.g. Private Banks, IT Services, Pharmaceuticals, Steel, FMCG, etc. |
| index_weight_pct | 0.2 – 4.5% | Estimated Nifty 100 index weight. For display only; not used in KPI calculations. |
| market_cap_category | Large Cap / Mid Cap | Classification at dataset creation time. |

| Broad Sector | Sub-Sectors Included | Companies |
| --- | --- | --- |
| Financials | Private Banks, Public Sector Banks, Life Insurance, General Insurance, Consumer Finance, Holding Cos, Speciality Finance 19 |  |
| Energy | Oil & Gas Refining, Oil & Gas Exploration, Power & Utilities, Renewable Energy, Gas Distribution, Power Transmission 15 |  |
| Information Technology | IT Services, Internet & Platforms | 6 |
| Consumer Discretionary | Automobiles, Two Wheelers, Auto Ancillaries, Retail, Gems & Jewellery, Airlines, Travel & Tourism 12 |  |
| Consumer Staples | FMCG, Food Products, Food & Beverages, Personal Products | 8 |
| Healthcare | Pharmaceuticals | 5 |
| Materials | Steel, Metals & Mining, Cement, Specialty Chemicals, Paints & Coatings | 8 |
| Industrials | Capital Goods, Defence Electronics, Defence & Aerospace, Engineering & Construction, Consumer Electricals 9 |  |
| Communication Services | Telecommunications, Internet & Platforms | 2 |
| Real Estate | Real Estate, Infrastructure | 3 |
| Conglomerates / Other | Diversified Conglomerates, Holding Companies | 5 |

6.2 stock_prices.xlsx — Monthly OHLCV Price History (Simulated)

| Column | Type | Range / Format | Notes |
| --- | --- | --- | --- |
| company_id | VARCHAR | NSE Ticker | FK → companies.id. |
| date | VARCHAR | YYYY-MM-DD | First calendar day of each month. Covers Jan 2020 – Dec 2024 (60 months). |
| open_price | NUMERIC | ■5 – ■18,000 | Simulated monthly opening price. For price trend and return charts. |
| high_price | NUMERIC | ■5 – ■19,000 | Monthly high. Always ≥ open and ≥ close. |
| low_price | NUMERIC | ■4 – ■17,500 | Monthly low. Always ≤ open and ≤ close. |
| close_price | NUMERIC | ■5 – ■18,000 | Monthly closing price. Primary field for return calculations. |
| volume | INTEGER | 100K – 50M | Simulated monthly traded volume in shares. |
| adjusted_close | NUMERIC | ■5 – ■18,000 | Same as close_price (no dividend adjustment in simulation). |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 14

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL 6.3 market_cap.xlsx — Annual Valuation Multiples

| Column | Type | Range | Notes |
| --- | --- | --- | --- |
| company_id | VARCHAR | NSE Ticker | FK → companies.id. |
| year | INTEGER | 2019–2024 | Calendar year. One row per company per year. |
| market_cap_crore | NUMERIC | ■5K–■15L Cr | Market capitalisation. Simulated. Use for EV, P/E, FCF yield denominator. |
| enterprise_value_crore | NUMERIC | ■4K–■17L Cr | EV = Mkt Cap + Net Debt (proxy). Simulated. |
| pe_ratio | NUMERIC | 8–80× | Price-to-Earnings. Simulated around sector norms. |
| pb_ratio | NUMERIC | 0.5–15× | Price-to-Book. Cross-check vs book_value in companies.xlsx. |
| ev_ebitda | NUMERIC | 5–40× | EV / EBITDA multiple. Use for sector valuation comparison. |
| dividend_yield_pct | NUMERIC | 0–4.5% | Annual dividend yield. Simulated. |

6.4 financial_ratios.xlsx — Pre-Computed KPI Table

| Column | Source | Formula / Notes |
| --- | --- | --- |
| company_id, year | All | Composite PK. |
| net_profit_margin_pct | P&L | net_profit / sales × 100. Negative allowed. |
| operating_profit_margin_pct | P&L | From opm_percentage source field. Cross-validate vs computed. |
| return_on_equity_pct | P&L+BS | net_profit / (equity_cap + reserves) × 100. |
| debt_to_equity | BS | borrowings / (equity_cap + reserves). 0 = debt-free. |
| interest_coverage | P&L | (op_profit + other_income) / interest. None if interest = 0. |
| asset_turnover | P&L+BS | sales / total_assets. |
| free_cash_flow_cr | CF | operating_activity + investing_activity (■ Cr). |
| capex_cr | CF | abs(investing_activity) — CapEx proxy (■ Cr). |
| earnings_per_share | P&L | eps source field (■). |
| book_value_per_share | BS+Co | (equity + reserves) / (equity_cap / face_value) (■). |
| dividend_payout_ratio_pct | P&L | dividend_payout source field (%). |
| total_debt_cr | BS | borrowings (■ Cr). |
| cash_from_operations_cr | CF | operating_activity (■ Cr). |

6.5 peer_groups.xlsx — Peer Comparison Groups

| Peer Group | Members | Benchmark |
| --- | --- | --- |
| Private Banks | HDFCBANK, ICICIBANK, AXISBANK, KOTAKBANK, INDUSINDBK | HDFCBANK |
| Public Banks | SBIN, BANKBARODA, CANBK, PNB | SBIN |
| IT Services | TCS, INFY, HCLTECH, TECHM, LTIM | TCS |
| Pharmaceuticals | SUNPHARMA, CIPLA, DRREDDY, DIVISLAB, TORNTPHARM | SUNPHARMA |
| Automobiles | MARUTI, TATAMOTORS, M&M, BAJAJ-AUTO, EICHERMOT, HEROMOTOCO, TVSMOTOR MARUTI |  |
| Life Insurance | LICI, HDFCLIFE, SBILIFE, ICICIPRULI | LICI |
| Oil & Gas | RELIANCE, ONGC, BPCL, IOC, GAIL | RELIANCE |
| Power & Utilities | NTPC, POWERGRID, TATAPOWER, ADANIPOWER, NHPC, JSWENERGY, ADANIGREEN NTPC |  |
| Steel & Metals | TATASTEEL, JSWSTEEL, JINDALSTEL, HINDALCO | TATASTEEL |
| FMCG | HINDUNILVR, ITC, BRITANNIA, DABUR, NESTLEIND, GODREJCP, TATACONSUMHINDUNILVR |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 15

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

| Peer Group | Members | Benchmark |
| --- | --- | --- |
| Consumer Finance | BAJFINANCE, CHOLAFIN, SHRIRAMFIN | BAJFINANCE |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 16

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL Foreign Keys, Join

7. Data Relationships & Entity Map 7.1 Entity-Relationship Summary

Paths & Coverage Matrix

| Parent Table | Parent Key | Child Table | Child Key | Cardinality | Join Note |
| --- | --- | --- | --- | --- | --- |
| companies | id (NSE ticker) | profitandloss | company_id | 1 : N | Up to 15 annual rows per company |
| companies | id | balancesheet | company_id | 1 : N | Up to 15 annual rows per company |
| companies | id | cashflow | company_id | 1 : N | Up to 14 annual rows per company |
| companies | id | analysis | company_id | 1 : 1 | Partial — ~8 companies have entries |
| companies | id | documents | company_id | 1 : N | 1–20 annual report links per company |
| companies | id | prosandcons | company_id | 1 : N | Partial — ~8 companies with entries |
| companies | id | sectors | company_id | 1 : 1 | All 92 companies covered |
| companies | id | stock_prices | company_id | 1 : N | 60 monthly rows per company |
| companies | id | market_cap | company_id | 1 : N | 6 annual rows (2019–2024) |
| companies | id | financial_ratios | company_id | 1 : N | Up to 14 annual rows per company |
| companies | id | peer_groups | company_id | M : N | A company can be in multiple groups |

7.2 Dataset Coverage Matrix

| Dataset | Companies Covered | Years Available | Completeness | Data Source |
| --- | --- | --- | --- | --- |
| companies | 92 / 92 (100%) | Snapshot only | Complete | Screener.in scrape |
| profitandloss | 92 / 92 | FY 2010–2024 | ~95% | Screener.in / BSE filings |
| balancesheet | 92 / 92 | FY 2010–2024 | ~97% | Screener.in / BSE filings |
| cashflow | 92 / 92 | FY 2010–2024 | ~91% | Screener.in / BSE filings |
| analysis | ~8 / 92 (9%) | Multi-period | Partial | Screener.in pre-computed metrics |
| documents | ~75 / 92 (82%) | Calendar 2010–24 | Partial | BSE India Annual Reports portal |
| prosandcons | ~8 / 92 (9%) | Snapshot only | Partial | Screener.in qualitative section |
| sectors | 92 / 92 | Snapshot | Complete | Created — GICS-style manual mapping |
| stock_prices | 92 / 92 | Jan 2020–Dec 2024 | Complete | Created — simulated OHLCV |
| market_cap | 92 / 92 | 2019–2024 | Complete | Created — simulated valuation |
| financial_ratios | 92 / 92 | FY 2010–2024 | ~93% | Created — computed from raw files |
| peer_groups | 46 / 92 (50%) | Snapshot | Partial | Created — manually defined groups |

7.3 Standard Join Pattern — Python / SQL

| Scenario | Join Logic |
| --- | --- |
|  | P&L + Balance Sheet for one year SELECT p.*, b.borrowings, b.total_assets FROM profitandloss p JOIN balancesheet b USING (company_id, year) |
| Full profile with sector | SELECT c.id, c.company_name, s.broad_sector, s.sub_sector FROM companies c JOIN sectors s ON c.id = s.company_id |
|  | CFO + Net Profit health checkSELECT p.company_id, p.year, p.net_profit, f.operating_activity FROM profitandloss p JOIN cashflow f USING (company_id, year) |
|  | Valuation multiples with earnings SELECT m.*, p.net_profit, p.eps FROM market_cap m JOIN profitandloss p USING (company_id, year) |
| Peer group ranking | SELECT r.company_id, r.return_on_equity_pct, RANK() OVER (PARTITION BY pg.peer_group_name ORDER BY r.return_on_equit |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 17

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL 7-Layer Data Platform

8. System Architecture

with 12 Analytical Modules

| Layer | Layer Name | Components | Technology |
| --- | --- | --- | --- |
| L1 | Raw Data Ingestion | Excel loader, URL validator, schema validator | Python — pandas, openpyxl, requests |
| L2 | ETL & Normalisation | Year normaliser, ticker normaliser, dedup engine | Python — pandas, custom ETL modules |
| L3 | Persistent Storage | SQLite database (10 tables) — core + supporting | SQLite 3.x — single-file, zero-config |
| L4 | Analytics Engine | Ratio engine, screener, comparator, capital classifierPython — pandas, NumPy, scipy.stats |  |
| L5 | Intelligence Layer | Peer percentiles, health scorer, NLP summarizer | Python — scikit-learn, regex, NLTK |
| L6 | Reporting Layer | PDF reports, Excel exports, chart generation | ReportLab, openpyxl, matplotlib, Plotly |
| L7 | Dashboard & API | Streamlit app (8 screens), REST API (16 endpoints)Streamlit, FastAPI, Uvicorn |  |

8.1 Technology Stack

| Category | Library / Tool | Version | Purpose |
| --- | --- | --- | --- |
| Data | pandas | ≥ 2.0 | DataFrame operations, Excel read/write, pivot tables |
| Data | NumPy | ≥ 1.24 | Vectorised KPI computation, growth rate arrays |
| Data | openpyxl | ≥ 3.1 | Read .xlsx files with header=1 for core datasets |
| Database | SQLite | 3.x | Single-file relational store; zero server overhead |
| Analytics | scipy | ≥ 1.11 | Statistical distributions, hypothesis tests (t-test, Mann-Whitney) |
| Analytics | scikit-learn | ≥ 1.3 | KMeans clustering, percentile ranking, scaler |
| Visualisation | matplotlib | ≥ 3.7 | Static charts for PDF reports |
| Visualisation | Plotly | ≥ 5.18 | Interactive charts for Streamlit dashboard |
| Dashboard | Streamlit | ≥ 1.30 | Multi-page web dashboard — no frontend code needed |
| API | FastAPI | ≥ 0.110 | REST API server with OpenAPI docs auto-generated |
| API | Uvicorn | ≥ 0.27 | ASGI server to run FastAPI |
| PDF | ReportLab | ≥ 4.1 | PDF document generation (all reports) |
| NLP | NLTK | ≥ 3.8 | Text tokenisation for qualitative analysis + pros/cons generation |
| NLP | regex | stdlib | Pattern extraction from analysis.xlsx text fields |
| Testing | pytest | ≥ 7.4 | Unit tests for ETL, KPI formulas, edge cases |
| Dev | Jupyter | ≥ 7.0 | Exploratory analysis notebook (not in production path) |
| Dev | black | ≥ 24.0 | Code formatting — PEP8 compliance |
| Dev | ruff | ≥ 0.4 | Linting — style and import checks |
| Dev | pre-commit | ≥ 3.7 | Git hooks: black + ruff run before every commit |
| Env | python-dotenv | ≥ 1.0 | Config via .env file — paths, thresholds, flags |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 18

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL Data Foundation,

9. Module Specifications — Modules 1–4 Module 1: Data Ingestion & ETL

Analytics Engine, Screener & Peer Comparison

Reads all 7 core + 5 supplementary Excel files, normalises fields, validates schemas, removes duplicates, and loads into a 10-table SQLite database. The foundation for all downstream modules.

Sprint: Sprint 1 (Days 1–7)

| # | Feature |  | Acceptance Criterion | Output |
| --- | --- | --- | --- | --- |
| 1.1 | Excel file loader with header=1 support |  | Loads all 7 core files with correct column headers; handles merged cells DataFrames |  |
| 1.2 | Ticker normaliser |  | company_id.str.strip().str.upper() on all tables; FK integrity passes Normalised IDs |  |
| 1.3 | Year label standardiser |  | Mar-23 → 2023-03 via normalize_year(); Mar / Dec FY handled Uniform year strings |  |
| 1.4 | Schema validator (16 rules) |  | Zero schema failures on reference dataset; failures logged to CSV validation_log.csv |  |
| 1.5 | Deduplication engine |  | No duplicate (company_id, year) pairs in time-series tables Clean tables |  |
| 1.6 | SQLite loader |  | All 10 tables written; rowcounts match source; FK constraints enabled nifty100.db |  |
| 1.7 | Load audit log |  | load_audit.csv: table, rows_in, rows_out, rejected, timestamp, runtime_s Audit file |  |
| Output |  | Detail |  |  |
| nifty100.db (SQLite) |  | 10 tables: companies, profitandloss, balancesheet, cashflow, analysis, documents, prosandcons, sectors, market_cap, stock_pri |  |  |
| load_audit.csv |  | Per-table load statistics for QA review. Row count, rejection count, runtime. |  |  |
| validation_failures.csv |  | All DQ rule violations with company_id, year, field, issue, severity (CRITICAL/WARNING). |  |  |

Module 2: Financial Ratio Engine

Computes 50+ KPIs for every company-year combination across all 14 available years. Handles all edge cases: division by zero, negative equity, debt-free companies, bank/NBFC D/E carve-out, and CAGR sign anomalies.

Sprint: Sprint 2 (Days 8–14)

| # | Feature / KPI |  | Formula | Edge Case |
| --- | --- | --- | --- | --- |
| 2.1 | Net Profit Margin |  | net_profit / sales × 100 | None if sales = 0 |
| 2.2 | Operating Profit Margin |  | operating_profit / sales × 100 | Cross-check vs opm_percentage |
| 2.3 | Return on Equity (ROE) |  | net_profit / (equity + reserves) × 100 | None if equity ≤ 0 |
| 2.4 | Return on Capital (ROCE) |  | (EBIT) / (equity + reserves + borrowings) × 100Exclude NBFC/Banks from D/E flag |  |
| 2.5 | Debt-to-Equity |  | borrowings / (equity + reserves) | 0 for debt-free; flag >5 for non-financials |
| 2.6 | Interest Coverage |  | (op_profit + other_income) / interest | None if interest = 0; 999 displayed as 'Debt Free' |
| 2.7 | Free Cash Flow |  | CFO + CFI | Negative allowed; flag if negative 3yr consecutive |
| 2.8 | CAGR (Revenue, PAT, EPS) |  | ((end/start)^(1/n) − 1) × 100 | Turnaround flag if base < 0 and end > 0 |
| 2.9 | Asset Turnover |  | sales / total_assets | None if total_assets = 0 |
| 2.10 | Capital Allocation Class |  | Sign pattern of CFO/CFI/CFF | 8 patterns → labels: Reinvest, Return, Distress, etc. |
| Output |  | Detail |  |  |
| financial_ratios table (SQLite) |  | 14 computed KPI columns per company-year; ~1,184 rows minimum |  |  |
| capital_allocation.csv |  | company_id, year, CFO_sign, CFI_sign, CFF_sign, pattern_label |  |  |
| ratio_edge_cases.log |  | Log of every CAGR turnaround, debt-free substitution, or division-by-zero |  |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 19

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

Module 3: Company Screener & Filter Engine

Multi-criteria stock screener with 15+ filterable metrics. Produces ranked result sets. Analyst configures thresholds via YAML config; no code changes needed to add new screening presets.

Sprint: Sprint 3 (Days 15–21)

| # | Feature |  | Criteria / Logic | Output |
| --- | --- | --- | --- | --- |
| 3.1 | Preset screeners (6 templates) |  | Quality: ROE>15%, D/E<1, FCF>0. Value: P/E<20, P/B<3. Growth: PAT CAGR >20% 5yr. Dividend: Yield>Ranked company list |  |
| 3.2 | Custom filter builder |  | Analyst defines thresholds per metric in YAML config (screener_config.yaml) Configurable |  |
| 3.3 | Ranking engine |  | RANK() OVER sector partition on composite score (50% profitability, 30% growth, 20% valuation) Score 0–100 |  |
| 3.4 | Sector-relative screener |  | Same thresholds normalised within broad_sector; flags outliers (>2 Peer-adjusted rank | σ or bottom decile) |
| 3.5 | Screener export (Excel + CSV) |  | Top-N results with all KPIs; sortable, formatted screener_output.xlsx |  |
| 3.6 | Multi-year trend filter |  | Filter companies where metric improved consecutively for N years Trend table |  |
| Output |  | Detail |  |  |
| screener_output.xlsx |  | Top results for each preset with 20+ KPIs displayed, colour-coded by threshold |  |  |
| screener_config.yaml |  | All screening thresholds; analysts edit this file to create custom screens |  |  |
| screener API endpoint |  | GET /api/v1/screener?min_roe=15&max_de=1&sector=IT → JSON response |  |  |

Module 4: Peer Comparison Engine

Compares companies within their peer group (from peer_groups.xlsx) across 20 metrics. Computes within-group percentile rank for every metric. Produces radar charts and comparison tables.

Sprint: Sprint 3 (Days 15–21)

| # | Feature |  | Logic | Output |
| --- | --- | --- | --- | --- |
| 4.1 | Intra-group percentile rank |  | PERCENT_RANK() OVER (PARTITION BY peer_group ORDER BY metric) Rank 0–1 per metric |  |
| 4.2 | Multi-metric radar chart |  | 8 axes: ROE, ROCE, NPM, D/E, FCF, PAT CAGR, Revenue CAGR, EPS CAGR Plotly radar / matplotlib polar |  |
| 4.3 | Side-by-side comparison table |  | Up to 5 companies: all 14 ratios, 5-year CAGR, capital allocation pattern Formatted HTML + PDF |  |
| 4.4 | Benchmark gap analysis |  | Metric_value vs benchmark_company in peer group; gap in absolute & pct Heatmap: green=above bench, red=below |  |
| 4.5 | Best-in-class detection |  | Company in top quartile (≥75th pctile) for ≥ | 6 of 10 metrics Badge table→ 'Best in Class' badge |
| 4.6 | Weak company detection |  | Bottom quartile (≤25th pctile) for ≥4 of 10 metrics Flag list | → 'Watch List' flag |
| Output |  | Detail |  |  |
| peer_comparison.xlsx |  | One sheet per peer group; 20 metrics, colour-coded percentile cells |  |  |
| radar_charts/ |  | One radar PNG per company showing performance vs peer group average |  |  |
| peer_percentiles table |  | SQLite: company_id, peer_group, metric, value, percentile_rank, year |  |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 20

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

10. Module Specifications — Modules 5–8 Module 5: Interactive Streamlit Dashboard

Dashboard, Valuation, Cash Flow Intelligence & Reports

8-screen web application. No authentication required for MVP. All screens load from SQLite. Deployed locally via `streamlit run app.py`. All charts are Plotly interactive; all tables are sortable.

Sprint: Sprint 4 (Days 22–28)

| # | Screen |  | Key Widgets / Features | Data Source |
| --- | --- | --- | --- | --- |
| 5.1 | Home / Overview |  | Nifty 100 summary KPIs: avg ROE, median P/E, sectors donut. Market health banner. companies + financial_ratios |  |
| 5.2 | Company Profile |  | Search by name/ticker. Company card: logo, description, KPI tiles (6 metrics), P&L chart, BS chart, CF bar All core tables |  |
| 5.3 | Financial Screener |  | Sidebar sliders for 10 metrics. Live-updating results table. CSV download button. financial_ratios + market_cap |  |
| 5.4 | Peer Comparison |  | Select peer group → | radar chart + side-by-side table. Toggle between years. peer_groups + financial_ratios |
| 5.5 | Trend Analysis |  | Select company + metric → | 10-year sparkline + YoY % change annotation. Multi-metric overlay mode. profitandloss + balancesheet |
| 5.6 | Sector Analysis |  | Sector selector → | bubble chart (revenue vs ROE, size = mkt cap). Sector median KPI bar chart. sectors + financial_ratios + market_cap |
| 5.7 | Capital Allocation Map |  | Treemap of 92 companies by capital pattern (8 categories). Click financial_ratios (CFO/CFI/CFF signs) | → drill down to company list. |
| 5.8 | Annual Reports |  | Company → year → | clickable BSE PDF link. Badge for missing reports. documents |
| Output |  | Detail |  |  |
| app.py + pages/ |  | Streamlit multi-page app. One file per screen under pages/ directory. |  |  |
| dashboard_guide.md |  | Analyst guide: how to navigate each screen, filter, and export data. |  |  |

Module 6: Valuation & Market Data Module

Uses market_cap.xlsx to compute and display valuation metrics. Provides historical P/E, P/B, EV/EBITDA trends. Flags companies trading above historical average multiples (potentially overvalued).

Sprint: Sprint 4 (Days 22–28)

| # | Feature |  | Logic | Output |
| --- | --- | --- | --- | --- |
| 6.1 | P/E Trend Chart |  | Line chart of P/E ratio across 2019–2024 per company Plotly chart |  |
| 6.2 | P/B vs ROE Scatter |  | X=P/B, Y=ROE, size=Mkt Cap, colour=sector for all 92 companies Scatter plot PNG |  |
| 6.3 | EV/EBITDA Comp Table |  | Current EV/EBITDA vs 5yr median, vs sector median. Flag if >20% above sector. Formatted table |  |
| 6.4 | Dividend Yield Ranker |  | Rank 92 companies by dividend yield. Filter by min yield threshold. Ranked list |  |
| 6.5 | FCF Yield Calculator |  | FCF / Market_Cap × 100. Rank descending. High FCF yield = value signal. Computed column |  |
| 6.6 | Overvaluation Flag |  | P/E > (sector_median × 1.5) → ' | Caution' badge. P/E < (sector_median × 0.7) Badge system → ' |
| Output |  | Detail |  |  |
| valuation_summary.xlsx |  | All 92 companies with current + 5yr median multiples, sector rank, badges |  |  |
| valuation_flags.csv |  | List of 'Caution' and 'Discount' flagged companies with rationale |  |  |

Discount' badge.

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 21

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

Module 7: Cash Flow Intelligence Module

Deep analysis of cash flow quality, CapEx intensity, FCF generation, and capital allocation patterns. Identifies companies with strong FCF compounding over 5+ years.

Sprint: Sprint 4–5 (Days 22–35)

| # | Feature |  | Logic | Output |
| --- | --- | --- | --- | --- |
| 7.1 | CFO Quality Score |  | CFO/PAT ratio > 1.0 across 5yr avg = 'High Quality Earnings'. <0.5 = 'Accrual Risk'. Quality badge |  |
| 7.2 | CapEx Intensity |  | CapEx / Revenue %. Light (<3%): asset-light. Heavy (>8%): capital intensive. Category label |  |
| 7.3 | FCF CAGR |  | FCF CAGR over 5yr and 10yr. Same CAGR rules as revenue (turnaround flag). CAGR column |  |
| 7.4 | FCF Conversion Rate |  | FCF / EBITDA. >60% = efficient. <30% = CapEx heavy. Ratio + tier |  |
| 7.5 | Debt Repayment Detection |  | CFF < 0 AND borrowings declining YoY → ' | Deleveraging' flag. Event flag |
| 7.6 | Distress Pattern |  | CFO < 0 AND CFF > 0 (equity/debt raise to fund operations) Alert badge | → 'Distress Signal'. |
| 7.7 | Capital Allocation Matrix |  | 8 CFO/CFI/CFF sign patterns → | descriptive labels (Reinvestor, Shareholder Returns, etc.) Pattern table |
| Output |  | Detail |  |  |
| cashflow_intelligence.xlsx |  | All companies with CFO quality score, FCF CAGR, CapEx intensity, capital allocation label |  |  |
| distress_alerts.csv |  | Companies flagged for distress pattern with supporting data |  |  |

Module 8: Automated PDF Report Generator

Generates company-level and portfolio-level PDF reports on demand using ReportLab. Two report types: Company Tearsheet (2 pages per company) and Portfolio Summary (all 92 companies, 1 page each).

Sprint: Sprint 5 (Days 29–35)

| # | Report Type |  | Contents | Frequency |
| --- | --- | --- | --- | --- |
| 8.1 | Company Tearsheet (2-page) |  | Page 1: KPI tiles, 10yr revenue & profit bar, ROE/ROCE trend line. Page 2: BS composition stacked bar, COn-demand via API |  |
| 8.2 | Portfolio Summary (1-page/co) |  | All 92 companies in one PDF: company name, sector, top 6 KPIs, trend arrow ( Weekly batch (Sprint 5) | ↑ ↓ → |
| 8.3 | Sector Report |  | Sector header page + all companies in sector. Sector median KPI table. Best/worst in sector highlighted. Monthly batch |  |
| 8.4 | Screener Output Report |  | Formatted PDF of screener results with charts, sorted by composite score. On-demand |  |
| 8.5 | Peer Group Report |  | Radar charts + side-by-side table for each of 11 peer groups. Weekly batch |  |
| Output |  | Detail |  |  |
| reports/tearsheets/ |  | 92 PDFs — one per company. Filename: <TICKER>_tearsheet.pdf |  |  |
| reports/portfolio/ |  | portfolio_summary_YYYYMMDD.pdf — all 92 companies in one document |  |  |
| reports/sector/ |  | 11 sector PDFs. Filename: <SECTOR>_report_YYYYMMDD.pdf |  |  |

) for 3yr direction.

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 22

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

11. Module Specifications — Modules 9–12 NLP, Clustering, API & Testing

Module 9: NLP & Qualitative Analysis Module

Parses and enriches qualitative text fields: about_company, pros, cons, analysis strings. Auto-generates pros/cons for companies with missing records using KPI-threshold rules. Extracts CAGR numbers from analysis.xlsx text fields.

Sprint: Sprint 5 (Days 29–35)

| # | Feature |  | Logic | Output |
| --- | --- | --- | --- | --- |
| 9.1 | Analysis text parser |  | Regex r'(\d+)\s*Years?:?\s*([\d.]+)%' on compounded_sales_growth, profit_growth, CAGR fields. Parsed numeric table: company, period, value |  |
| 9.2 | Auto pros/cons generator |  | Rule engine: 12 pro rules (ROE>20%, FCF positive 5yr, D/E=0, revenue CAGR>15%, etc.) + 12 con rules (pros_cons_generated.csv |  |
| 9.3 | Business description tagger |  | Classify about_company text into sector tags using keyword matching. Confirm vs sectors.xlsx. Tag validation report |  |
| 9.4 | Sentiment scorer |  | Basic polarity scoring on pros (positive) and cons (negative) text using NLTK SentimentIntensityAnalyzer. Sentiment score per entry |  |
| 9.5 | CAGR cross-validator |  | Compare parsed analysis.xlsx CAGR vs Ratio Engine computed CAGR. Flag >5% divergence. cross_validation.csv |  |
| Output |  | Detail |  |  |
| pros_cons_generated.csv |  | company_id, type (pro/con), rule_triggered, text, confidence_pct. Auto-fills gaps for 84 companies. |  |  |
| analysis_parsed.csv |  | Structured: company_id, metric_type, period_years, value_pct for all analysis.xlsx rows. |  |  |

Module 10: Statistical Analysis & Clustering Module

Uses scikit-learn for KMeans clustering of companies by financial profile. Computes portfolio-level statistics, correlation matrices, and outlier detection. Provides insight into hidden company groupings.

Sprint: Sprint 5–6 (Days 29–42)

| # | Feature |  | Logic | Output |
| --- | --- | --- | --- | --- |
| 10.1 | KMeans clustering (5 clusters) |  | Features: ROE, D/E, Revenue CAGR, FCF CAGR, OPM. StandardScaler + KMeans(n=5). Elbow method tcluster_labels.csv: company_id, cluster_id, cluster_name |  |
| 10.2 | Cluster profiling |  | Mean/median of each feature per cluster. Assign descriptive labels: High-Quality Growth, Defensive DividenCluster profile table |  |
| 10.3 | Correlation matrix |  | Pearson correlation of 10 KPIs across all 92 companies × latest year. Heatmap output. correlation_heatmap.png |  |
| 10.4 | Outlier detection |  | Z-score per metric per sector. ¦Z¦>3 → ' | Outlier' flag. Company-level outlier report. outlier_report.csv |
| 10.5 | Portfolio statistics |  | Distribution of ROE, D/E, P/E across Nifty 100. P10/P25/P50/P75/P90 percentile table. portfolio_stats.csv |  |
| Output |  | Detail |  |  |
| cluster_labels.csv |  | company_id, cluster_id (0–4), cluster_name, distance_from_centroid |  |  |
| portfolio_stats.csv |  | Metric, P10, P25, P50, P75, P90, Mean, Std for all 92 companies |  |  |
| outlier_report.csv |  | company_id, metric, value, z_score, sector, sector_mean, sector_std |  |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 23

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

Module 11: REST API Module

FastAPI server exposing 16 endpoints. Auto-generates OpenAPI documentation at /docs. All responses are JSON. API is consumed by the Streamlit dashboard for real-time data queries.

Sprint: Sprint 6 (Days 36–42)

| # | Endpoint |  | Method | Description |
| --- | --- | --- | --- | --- |
| 11.1 | /api/v1/companies |  | GET | List all 92 companies with id, name, sector. Supports ?secto |
| 11.2 | /api/v1/companies/{ticker} |  | GET | Full company profile: KPIs, pros/cons, sector, description. |
| 11.3 | /api/v1/companies/{ticker}/pl |  | GET | P&L history for a company. Supports ?from_year= ?to_year |
| 11.4 | /api/v1/companies/{ticker}/bs |  | GET | Balance sheet history. Same year filters. |
| 11.5 | /api/v1/companies/{ticker}/cashflow |  | GET | Cash flow history. Same year filters. |
| 11.6 | /api/v1/companies/{ticker}/ratios |  | GET | All 14 pre-computed KPIs per year for one company. |
| 11.7 | /api/v1/companies/{ticker}/tearsheet |  | GET | Returns pre-generated tearsheet PDF (binary download). |
| 11.8 | /api/v1/screener |  | GET | Screener: ?min_roe=&max_de=&sector=&min_cagr= |
| 11.9 | /api/v1/sectors |  | GET | List all 11 sectors with company count and median KPIs. |
| 11.10 | /api/v1/sectors/{sector}/companies |  | GET | All companies in a sector with KPI summary. |
| 11.11 | /api/v1/peers/{group_name} |  | GET | All companies in a peer group with percentile ranks. |
| 11.12 | /api/v1/companies/{ticker}/peers/compare |  | GET | Radar data: company vs peer group average for 8 metrics. |
| 11.13 | /api/v1/market-cap/{ticker} |  | GET | Historical valuation multiples (P/E, P/B, EV/EBITDA) 2019–2 |
| 11.14 | /api/v1/portfolio/stats |  | GET | Portfolio-level statistics: P10–P90 for all 10 core KPIs. |
| 11.15 | /api/v1/companies/{ticker}/documents |  | GET | Annual report links for a company. |
| 11.16 | /api/v1/health |  | GET | Server health check. Returns DB row counts and server upti |
| Output |  | Detail |  |  |
| api/main.py |  | FastAPI app. All routes in routers/ directory. One router file per module. |  |  |
| openapi.json |  | Auto-exported OpenAPI 3.0 spec. Import into Postman for API testing. |  |  |

→ ran

Module 12: Testing & Quality Assurance Module

pytest test suite with 60+ test cases covering: ETL correctness, KPI formula accuracy, API endpoint responses, data quality rule coverage. CI-style: all tests must pass before code is merged.

Sprint: Sprint 6 (Days 36–45)

| # | Test Category |  | Test Cases | Pass Criterion |
| --- | --- | --- | --- | --- |
| 12.1 | ETL Tests |  | year_normaliser (20 cases), ticker_normaliser (15 cases), dedup (5 cases), load_audit completeness (5 casAll 45 ETL tests pass |  |
| 12.2 | KPI Formula Tests |  | ROE with positive equity, ROE with negative equity (None), D/E for debt-free (0), ICR for interest=0 (None),All 20 formula tests pass |  |
| 12.3 | DQ Rule Tests |  | Each of 14 DQ rules triggered on crafted violation records; severity correct 14/14 rules trigger correctly |  |
| 12.4 | API Tests |  | /health returns 200; /companies returns 92 records; /screener with valid filters returns ranked list; invalid tickAll 10 API tests pass |  |
| 12.5 | Regression Tests |  | After any schema change, run full suite. No previously-passing test should fail. Zero regressions |  |
| Output |  | Detail |  |  |
| tests/ |  | pytest test directory. Structured: tests/etl/, tests/kpi/, tests/api/, tests/dq/ |  |  |
| pytest_report.html |  | HTML report with pass/fail counts, runtime per test, failure traceback for failed tests |  |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 24

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL 6 Sprints × 7–8 Days

12. 45-Day Sprint Plan

— Day-by-Day Task Breakdown

| Sprint | Days | Theme | Modules | Exit Criteria |
| --- | --- | --- | --- | --- |
| Sprint 1 | Days 01–07 | Data Foundation | Module 1 | nifty100.db built; all 10 tables loaded; load_audit.csv shows zero CRITIC |
| Sprint 2 | Days 08–14 | Ratio Engine | Module 2 | financial_ratios table populated for 92 × 14yr; 60+ KPIs computed; all 20 |
| Sprint 3 | Days 15–21 | Screener & Peers | Modules 3–4 | 6 preset screeners operational; peer percentile table built for all 11 group |
| Sprint 4 | Days 22–28 | Dashboard & Valuation | Modules 5–6 | Streamlit app running on localhost:8501; all 8 screens navigable; valuati |
| Sprint 5 | Days 29–35 | Intelligence & Reports | Modules 7–9 | 92 company tearsheet PDFs generated; pros_cons_generated.csv comp |
| Sprint 6 | Days 36–45 | API, ML & QA | Modules 10–12 | All 16 API endpoints return correct data; 60+ pytest tests pass; cluster_la |

Sprint 1 — Data Foundation (Days 1–7)

| Day | Tasks | Deliverable |
| --- | --- | --- |
| D01 | Set up project directory structure (data/, src/etl/, src/analytics/, src/api/, src/dashboard/, tests/, reports/). Create venv; install all dependencies; configure .enrequirements.txt, .env.template |  |
| D02 | Write Excel loader with header=1 support for all 7 core files. Write normalize_year() and normalize_ticker() functions. Unit tests: 20 cases each. etl/loader.py, tests/etl/test_normalise.py |  |
| D03 | Implement schema validator (16 DQ rules). Run against all 7 files. Log failures to validation_failures.csv. Review with team lead. etl/validator.py, validation_failures.csv |  |
| D04 | Build SQLite schema (CREATE TABLE statements for 10 tables with FK constraints). Write loader to insert normalised DataFrames. db/schema.sql, db/loader.py |  |
| D05 | Load all 5 supplementary files. Run full load for all 12 files. Generate load_audit.csv. nifty100.db, load_audit.csv |  |
| D06 | Data quality review: manually check 5 random companies across all time-series tables. Fix any loader bugs. Re-run load. DQ review notes in team channel |  |
| D07 | Write 10 SQL exploratory queries (row counts, nulls, year coverage per company). Sprint retrospective. Update task board. exploratory_queries.sql, sprint1_retro.md |  |

Sprint 2 — Ratio Engine (Days 8–14)

| Day | Tasks | Deliverable |
| --- | --- | --- |
| D08 | Implement profitability ratios: NPM, OPM, ROE, ROCE. Edge cases: negative equity (None), zero sales (None). Cross-validate OPM vs source. analytics/ratios.py |  |
| D09 | Implement leverage + efficiency ratios: D/E (bank carve-out), ICR (debt-free substitution), Asset Turnover. Write tests. tests/kpi/test_leverage.py |  |
| D10 | Implement CAGR engine: Revenue CAGR, PAT CAGR, EPS CAGR for 3yr, 5yr, 10yr windows. Turnaround flag logic. analytics/cagr.py |  |
| D11 | Implement cash flow KPIs: FCF, CFO Quality Score, CapEx Intensity, FCF Conversion, capital allocation pattern (8 classes). analytics/cashflow_kpis.py |  |
| D12 | Populate financial_ratios table in SQLite for all 92 companies × all years. Run validation: compare sample to manual Excel calculations. Updated financial_ratios table |  |
| D13 | Implement ROCE for banks/NBFCs: sector-relative approach. Cross-check vs roce_percentage in companies.xlsx. Log anomalies. sector_roce_notes.csv |  |
| D14 | Run all 20 KPI formula tests. Fix failures. Write ratio_edge_cases.log. Sprint retrospective. All KPI tests green, sprint2_retro.md |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 25

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

Sprint 3 — Screener & Peer Comparison (Days 15–21)

| Day | Tasks | Deliverable |
| --- | --- | --- |
| D15 | Build custom filter engine: load screener_config.yaml; apply threshold filters to financial_ratios via pandas query. src/screener/engine.py |  |
| D16 | Implement 6 preset screeners. Test each preset on the full 92-company universe. Verify results make business sense. 6 screener presets in config |  |
| D17 | Build ranking engine: composite score (50/30/20 weights). Sector-relative normalisation. Export to screener_output.xlsx. screener_output.xlsx |  |
| D18 | Build peer group module: load peer_groups.xlsx; compute PERCENT_RANK per metric per group for all 11 groups. analytics/peer.py, peer_percentiles table |  |
| D19 | Generate radar chart data for each company-peer group pair. Plot Plotly radar PNG for each company. reports/radar_charts/ (92 PNGs) |  |
| D20 | Generate peer_comparison.xlsx: one sheet per peer group, all metrics, colour-coded cells. peer_comparison.xlsx |  |
| D21 | Run all DQ rule tests. Fix failures. Sprint retrospective. | All tests green, sprint3_retro.md |

Sprint 4 — Dashboard & Valuation (Days 22–28)

| Day | Tasks | Deliverable |
| --- | --- | --- |
| D22 | Scaffold Streamlit app: main app.py + pages/ directory. Shared data loader (load_db() function). Style config (sidebar logo, colour theme). app.py, pages/ skeleton |  |
| D23 | Build Home screen (5.1) and Company Profile screen (5.2): ticker search, KPI tiles, 10yr bar charts. pages/01_home.py, pages/02_profile.py |  |
| D24 | Build Screener screen (5.3): sidebar sliders, live table, CSV download. Peer Comparison screen (5.4): group selector, radar. pages/03_screener.py, pages/04_peer.py |  |
| D25 | Build Trend Analysis (5.5), Sector Analysis (5.6), Capital Allocation Map (5.7), Annual Reports (5.8). pages/05–08.py |  |
| D26 | Build Valuation module: valuation_summary.xlsx, overvaluation flags, FCF yield column. Integrate valuation screen if time permits. valuation_summary.xlsx |  |
| D27 | Dashboard integration testing: test all 8 screens with 10 random tickers. Fix chart sizing, overflow, and missing-data edge cases. Test log: dashboard_qa.md |  |
| D28 | Sprint retrospective. Update README.md with app run instructions (streamlit run app.py). Record screen walkthrough video (optional). README.md update, sprint4_retro.md |  |

Sprints 5–6 — Intelligence, Reports, API & QA (Days 29–45) Summary

| Days | Theme | Key Daily Tasks | Exit Gate |
| --- | --- | --- | --- |
| D29–30 | NLP Module | Parser for analysis.xlsx CAGR text. Auto pros/cons generator (12 pro + 12 con rules). pros_cons_generated.csv: 92 companies |  |
| D31–32 | Cash Flow Intelligence | CFO quality score, CapEx intensity, distress pattern flagging, capital allocation matrix. cashflow_intelligence.xlsx |  |
| D33–35 | PDF Report Generator | Company Tearsheet (2-page × 92). Sector reports (11). Portfolio summary. All reports in reports/ dir. 92 tearsheets + 11 sector PDFs |  |
| D36–37 | KMeans Clustering | StandardScaler + KMeans(n=5). Elbow plot. Assign cluster labels. Correlation matrix heatmap. cluster_labels.csv, heatmap.png |  |
| D38–40 | FastAPI Server | 16 endpoints in api/ directory. Uvicorn server. OpenAPI docs at /docs. Postman collection exported. openapi.json, postman_collection.json |  |
| D41–42 | Full Test Suite | 60+ pytest tests across 4 categories. Fix failures. Generate HTML test report. pytest_report.html: all green |  |
| D43 | Integration Testing | End-to-end: API → | Dashboard data flow. Load test with 10 concurrent screener queries. Fix bottlenecks. Load test results in perf_notes.md |
| D44 | Documentation | Update all docstrings. Write analyst_guide.pdf (how to use screener + dashboard). Review project doc. analyst_guide.pdf |  |
| D45 | Final Sign-Off | Run acceptance checklist (23 gates). Present to team lead. Archive final deliverables to output/ dir. Signed acceptance_checklist.pdf |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 26

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

13. KPI Reference — 50+ Financial Metrics

Formulas,

Benchmarks, Edge Cases & Warning Flags

| KPI | Category | Formula | Benchmark | Edge Case / Warning Flag |
| --- | --- | --- | --- | --- |
| Net Profit Margin | Profitability | net_profit / sales × 100 |  | >10% = good; >20% = excellent Non if sales=0. Negative allowed. |
| Operating Profit Margin | Profitability | operating_profit / sales × 100 |  | >15% = good; >25% = excellent Cross-check vs opm_percentage field ±1%. |
| EBIT Margin | Profitability | (operating_profit − depreciation) / sales × 100>12% preferred |  | Excludes other_income to get core ops only. |
| Return on Equity (ROE) | Returns | net_profit / (equity + reserves) × 100 |  | >15% = good; >20% = excellent Non if equity+reserves |
| Return on Capital (ROCE) | Returns | EBIT / (equity + reserves + borrowings) × 100>15% = good; >25% = excellent Bank carve-out: use sector-relative benchmark. |  |  |
| Return on Assets (ROA) | Returns | net_profit / total_assets × 100 |  | >5% = good; >10% = excellent None if total_assets = 0. |
| Debt-to-Equity (D/E) | Leverage | borrowings / (equity + reserves) |  | <1.0 = healthy; <0.5 = conservative 0 = debt-free. Flag >5 for non-financials. |
| Interest Coverage (ICR) | Leverage | (op_profit + other_income) / interest | >3× = safe; >5× = strongNone if interest=0 | → |
| Net Debt | Leverage | borrowings − investments − cash | < 0 = net cash positive | investments used as liquid asset proxy. |
| Net Debt / EBITDA | Leverage | net_debt / operating_profit | <2× = healthy; >4× = stressed None if EBITDA < 0. |  |
| Asset Turnover | Efficiency | sales / total_assets |  | >1× = efficient. Asset-light >2× None if total_assets = 0. |
| Fixed Asset Turnover | Efficiency | sales / fixed_assets | >3× = good | None if fixed_assets = 0 (service cos). |
| Working Capital Days | Efficiency | (other_asset − other_liabilities) / sales × 365 | Lower = better | >180 days = slow collections flag. |
| Inventory Turnover | Efficiency | sales / (fixed_assets proxy) | Sector-dependent | Proxy only — no raw inventory field. |
| Revenue CAGR (3yr) | Growth | (sales_t / sales_{t-3})^(1/3) − 1 |  | >10% = healthy; >20% = fast Turnaround flag if base < 0. |
| Revenue CAGR (5yr) | Growth | (sales_t / sales_{t-5})^(1/5) − 1 |  | >12% = healthy; >25% = strong Turnaround flag if base < 0. |
| Revenue CAGR (10yr) | Growth | (sales_t / sales_{t-10})^(1/10) − 1 |  | >10% sustained = excellent Turnaround flag. None if <10yr history. |
| PAT CAGR (3yr) | Growth | (net_profit_t / net_profit_{t-3})^(1/3) − 1 |  | >15% = healthy; >25% = strong Turnaround flag. More volatile than revenue. |
| PAT CAGR (5yr) | Growth | (net_profit_t / net_profit_{t-5})^(1/5) − 1 | >15% = healthy; >30% = excellent Turnaround flag. |  |
| EPS CAGR (5yr) | Growth | (eps_t / eps_{t-5})^(1/5) − 1 | >12% = healthy | Must align with PAT CAGR unless share count c |
| Free Cash Flow | Cash Quality | operating_activity + investing_activity | > 0 = generating cash | Negative 3yr consecutive |
| CFO / PAT Ratio | Cash Quality | operating_activity / net_profit |  | >1.0 = high quality earnings <0.5 = accrual risk. None if net_profit = 0. |
| CapEx Intensity | Cash Quality | abs(investing_activity) / sales × 100 |  | <3% = asset-light; >8% = capital intensive investin_activity proxy — may include non-CapEx |
| FCF Conversion Rate | Cash Quality | FCF / operating_profit × 100 |  | >60% = efficient; <30% = heavy None if operating_profit = 0. |
| FCF Yield | Valuation | FCF / market_cap_crore × 100 | >3% = attractive | Requires market_cap table join. |
| Price-to-Earnings (P/E) | Valuation | market_cap / net_profit | 15–25× = fair for India large caps None if net_profit | ≤ |
| Price-to-Book (P/B) | Valuation | market_cap / (equity + reserves) |  | >3× = expensive for value investors Varies widely by sector: IT >8×, utilities <2×. |
| EV/EBITDA | Valuation | enterprise_value / operating_profit | 12–18× = fair for Indian large caps None if EBITDA < 0. |  |
| Dividend Yield | Valuation | dividend_yield_pct from market_cap table |  | >2% = dividend-paying; >4% = high yield Requires market_cap table. |
| Dividend Payout Ratio | Profitability | dividend_payout from P&L table | 30–60% = balanced | Flag >100% (paying more than earned). |
| Book Value Per Share | Valuation | (equity + reserves) / (equity_cap / face_value)>1 always. Rising trend = good Computed — cross-check vs companies.book_v |  |  |
| Earnings Per Share (EPS) | Profitability | eps from P&L table | Rising trend preferred | Dilution risk if equity issuance ongoing. |
| Capital Allocation: Reinvestor | Qualitative | CFO>0, CFI<0, CFF<0 | Ideal: paying debt + investing from ops Pattern: (+, | −, −) |
| Capital Allocation: Shareholder Returns Qualitative |  | CFO>0, CFI<0, CFF<0 (dividends) | Stable mature company Pattern: (+, | −, − |
| Capital Allocation: Distress | Qualitative | CFO<0, CFF>0 | Raising funds to fund ops — red flag Pattern: ( | −, ?, +) |
| Composite Quality Score | Composite | 0.3×ROE_score + 0.25×FCF_score + 0.25×ROCE_score + 0.20×DE_score 70–100 = excellent; 40–70 = moderate Normalised 0–100 using P10/P90 winsorisation. |  |  |

≤ 0.

display 'Debt Free'. Flag if <

→ 'FCF Concern' flag.

0. Compare within sector.

) same as above — sub-classify b

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 27

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

16 Validation Rules —

14. Data Quality Rules

Applied at ETL Load

Time

| Rule ID | Rule Name | Condition | Severity | Action |
| --- | --- | --- | --- | --- |
| DQ-01 | Company PK Uniqueness | len(companies) == companies.id.nunique()CRITICAL |  | Halt load. Investigate duplicate ticker. |
| DQ-02 | Annual PK Uniqueness | No duplicate (company_id, year) in P&L, BS, CF tables CRITICAL |  | Deduplicate: keep last occurrence. Log all duplicates. |
| DQ-03 | FK Integrity | All company_id in child tables exist in companies.id CRITICAL |  | Reject orphan rows. Log to validation_failures.csv. |
| DQ-04 | Balance Sheet Balance | ¦total_assets − total_liabilities¦ / total_assets < 0.01 WARNING |  | Flag row. Do not reject. Analyst review required. |
| DQ-05 | OPM Cross-Check | ¦opm_percentage − (op_profit/sales×100)¦ < 1.0 WARNING |  | Flag row. Use computed OPM in Ratio Engine; keep source fo |
| DQ-06 | Positive Sales | sales > 0 for all non-bank companies | WARNING | Flag rows with sales ≤ 0. Exclude from growth CAGR. |
| DQ-07 | Year Format | After normalize_year(), all values match r'^\d{4}-\d{2}$' CRITICAL |  | Reject row if unparseable. Log raw value. |
| DQ-08 | Ticker Format | company_id = company_id.strip().upper(). Length: 2–12 chars. CRITICAL Normalise silently. If length out of range, reject. |  |  |
| DQ-09 | Net Cash Check | ¦net_cash_flow − (CFO+CFI+CFF)¦ ≤ 10 ( | ■ | WARNING Cr tolerance) Flag and compute net_cash_flow from components if mismatc |
| DQ-10 | Non-Negative Fixed Assets | fixed_assets ≥ 0 | WARNING | Negative fixed_assets → coerce to 0 and log. |
| DQ-11 | Tax Rate Range | 0 ≤ tax_percentage ≤ 60 | WARNING | Flag out-of-range. Can indicate one-off deferred tax reversal. |
| DQ-12 | Dividend Payout Cap | dividend_payout ≤ 200 (pct) | WARNING | Flag >200% as likely data entry error. Analyst confirm. |
| DQ-13 | URL Validity (documents) | requests.head(Annual_Report).status_code == 200 WARNING |  | Log 404 URLs. Do not reject row — URL decay expected over |
| DQ-14 | EPS Sign Consistency | eps > 0 if net_profit > 0 | WARNING | Flag mismatch (may indicate adjustments). Use net_profit/sha |
| DQ-15 | BSE/ASE Balance (ext.) | total_liabilities == total_assets (strict, after DQ-04 flag) INFO |  | Informational counter. Flag in load_audit only. |
| DQ-16 | Coverage Check | Each company has ≥ 5 years of P&L, BS, CF records WARNING |  | Flag companies with < 5yr history. Exclude from CAGR if < 3y |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 28

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

15. API Specification 16 REST Endpoints — FastAPI / OpenAPI 3.0

| Endpoint | Method | Query Params | Response Fields | Status Codes |
| --- | --- | --- | --- | --- |
| /api/v1/companies | GET |  | sector, market_cap_category, search (string) id, company_name, broad_sector, sub_sector, roe_pct, roce_pct 200 OK, 400 Bad Request |  |
| /api/v1/companies/{ticker} | GET | year (optional; default=latest) | Full company object: all companies fields + latest KPIs + sector 200 OK, 404 Not Found |  |
| /api/v1/companies/{ticker}/pl | GET |  | from_year (YYYY-MM), to_year (YYYY-MM) Array of P&L rows for company. All 13 numeric fields. 200 OK, 404 Not Found |  |
| /api/v1/companies/{ticker}/bs | GET | from_year, to_year | Array of balance sheet rows. All 11 numeric fields. 200 OK, 404 Not Found |  |
| /api/v1/companies/{ticker}/cashflow | GET | from_year, to_year | Array of cash flow rows. CFO, CFI, CFF, net_cash_flow. 200 OK, 404 Not Found |  |
| /api/v1/companies/{ticker}/ratios | GET | year (optional; default=all) | Array: company_id, year + 14 computed KPI fields. 200 OK, 404 Not Found |  |
| /api/v1/companies/{ticker}/tearsheet | GET | — | Binary PDF stream (application/pdf). Triggers download. 200 OK, 404 Not Found |  |
| /api/v1/screener | GET |  | min_roe, max_de, min_fcf, sector, min_rev_cagr_5yr, min_pat_cagr_5yr, max_pe Array of matching companies: ticker, name, sector, all filter KPIs, composite score 200 OK, 400 Bad Request |  |
| /api/v1/sectors | GET | — | Array: sector_name, company_count, median_roe, median_pe, median_de 200 OK |  |
| /api/v1/sectors/{sector}/companies | GET | year (default=latest) | Array of companies in sector with top 8 KPIs each. 200 OK, 404 Not Found |  |
| /api/v1/peers/{group_name} | GET | year (default=latest) | Array of companies + percentile rank for each of 10 metrics. 200 OK, 404 Not Found |  |
| /api/v1/companies/{ticker}/peers/compareGET |  | year (default=latest) | Radar data: 8 axis metrics for company + group average + benchmark. 200 OK, 404 Not Found |  |
| /api/v1/market-cap/{ticker} | GET | from_year, to_year | Array: year, market_cap_crore, pe_ratio, pb_ratio, ev_ebitda, div_yield. 200 OK, 404 Not Found |  |
| /api/v1/portfolio/stats | GET | year (default=latest) | P10–P90 table for 10 KPIs across all 92 companies. 200 OK |  |
| /api/v1/companies/{ticker}/documents | GET | from_year, to_year | Array: year, Annual_Report URL, is_url_valid (boolean). 200 OK, 404 Not Found |  |
| /api/v1/health | GET | — | status, db_row_counts (all 10 tables), uptime_seconds, version. 200 OK, 503 DB Unavailable |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 29

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

12 Project Risks —

16. Risk Register

Likelihood, Impact &

Mitigation Plan

| Risk ID | Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R-01 | Missing years of data for some companies (coverage < 5yr) High Medium |  |  | DQ-16 flags companies with < 5yr. Exclude from CAGR. Supplement with public filing |
| R-02 | BSE Annual Report URLs returning 404 (link decay) High Low |  |  | DQ-13 validates URLs on load. Log failures. Dashboard shows 'Report unavailable' gr |
| R-03 | analysis.xlsx text parsing fails for new formats Medium |  | Medium | Regex tested for 5 format variants. Unknown formats logged to parse_failures.csv for |
| R-04 | Bank / NBFC D/E misclassification skews screener results Medium High |  |  | sectors.broad_sector used to carve out Financials from D/E filter. Tested on 19 financi |
| R-05 | Negative equity companies breaking ROE formula Medium High |  |  | ROE = None if equity+reserves ≤ 0. Logged. Excluded from screener ROE filter. |
| R-06 |  |  |  | Simulated stock_prices / market_cap values cause incorrect real conclusions Low High All simulated datasets are clearly labelled SIMULATED in column comments and dash |
| R-07 | CAGR turnaround flag not applied Low | → | misleading growth metrics High | CAGR engine explicitly checks base year sign. Turnaround flag stored in ratio column |
| R-08 | ReportLab LayoutError on very long text cells overflowing frames Medium Medium |  |  | All tables use WORDWRAP; cells > 200 chars are truncated with ellipsis. Tested on w |
| R-09 |  |  |  | Streamlit slows down with full 92-company dataset on low-spec hardware Low Medium SQLite queries are cached with @st.cache_data (TTL=600s). Max screener result set |
| R-10 | Peer group coverage is partial (46/92 companies) Medium Medium |  |  | Peer module gracefully handles companies not in any group: returns 'No peer group a |
| R-11 |  |  |  | pros/cons auto-generation produces low-confidence or incorrect flags Medium Low Confidence score displayed alongside auto-generated entries. Threshold: only show if |
| R-12 | FastAPI / Uvicorn port conflict on analyst machine Low Low |  |  | Default port 8000. .env file contains PORT variable. README documents port change |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 30

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

23 Mandatory

Deliverables —

17. Deliverables Checklist

Sign-Off Required on

Day 45

| # | Deliverable | Format | Owner Sprint | Sign-Off Criteria |
| --- | --- | --- | --- | --- |
| D-01 | nifty100.db | SQLite file | S1 | All 10 tables populated. rowcounts match source. FK constraints pass. |
| D-02 | load_audit.csv | CSV | S1 | All 12 files loaded. Zero CRITICAL failures. |
| D-03 | validation_failures.csv | CSV | S1 | All DQ rule violations documented with severity. |
| D-04 | exploratory_queries.sql | SQL | S1 | 10+ queries covering coverage, nulls, year distribution. |
| D-05 | financial_ratios table | SQLite table | S2 | 14 KPI columns. 1,184+ rows. KPI formula tests pass. |
| D-06 | capital_allocation.csv | CSV | S2 | All 92 companies × all years with pattern label. |
| D-07 | screener_output.xlsx | Excel | S3 | 6 preset screener results with composite score + 20 KPIs. |
| D-08 | screener_config.yaml | YAML | S3 | All 15 filter thresholds defined. Analyst-editable. |
| D-09 | peer_comparison.xlsx | Excel | S3 | 11 sheets. Colour-coded percentile cells. 20 metrics. |
| D-10 | radar_charts/ (92 PNGs) | PNG files | S3 | One radar chart per company. 8 axes. Peer avg overlay. |
| D-11 | Streamlit Dashboard (app.py) | Python app | S4 | 8 screens. All navigable. CSV export functional. |
| D-12 | valuation_summary.xlsx | Excel | S4 | All 92 companies. P/E, P/B, EV/EBITDA, flags. |
| D-13 | cashflow_intelligence.xlsx | Excel | S5 | CFO quality score, FCF CAGR, CapEx intensity, distress flags. |
| D-14 | pros_cons_generated.csv | CSV | S5 | 92 companies. Rule-triggered. Confidence > 60%. |
| D-15 | analysis_parsed.csv | CSV | S5 | Structured CAGR numbers from analysis.xlsx. Cross-validated. |
| D-16 | Company Tearsheets (92 PDFs) | PDF files | S5 | 2 pages per company. All 92 companies. In reports/tearsheets/ |
| D-17 | Sector Reports (11 PDFs) | PDF files | S5 | One per broad sector. KPI table + company list. |
| D-18 | Portfolio Summary PDF | PDF | S5 | All 92 companies, 1-page each in one document. |
| D-19 | cluster_labels.csv | CSV | S6 | 5 clusters. All 92 companies assigned. Cluster names labelled. |
| D-20 | FastAPI Server (api/) | Python app | S6 | 16 endpoints. openapi.json exported. /health returns 200. |
| D-21 | pytest_report.html | HTML | S6 | 60+ tests. All green. Runtime < 120 seconds total. |
| D-22 | analyst_guide.pdf | PDF | S6 | Screener usage guide + dashboard navigation. 10–15 pages. |
| D-23 | acceptance_checklist.pdf | PDF | S6 | 23 deliverables reviewed and signed off. Date stamped. |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 31

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL 20 Non-Negotiable

18. Acceptance Criteria

Quality Gates — All Must Pass Before Sign-Off

| Gate | Area | Criterion | Tested By |
| --- | --- | --- | --- |
| AC-01 | Data Coverage | 92 companies present in companies table. No extra or missing tickers. SELECT COUNT(*) FROM companies | → 92 |
| AC-02 | Time Coverage | ≥ 90% of companies have ≥ | 10 years of P&L, BS, CF records. DQ coverage query in load_audit.csv |
| AC-03 | Schema Integrity | All FK relationships intact. PRAGMA foreign_key_check returns 0 rows. SQLite FK check command |  |
| AC-04 | KPI Completeness | financial_ratios table has ≥ 1 | ,100 rows. All 14 KPI columns populated. SELECT COUNT(*) FROM financial_ratios |
| AC-05 | CAGR Accuracy | Revenue CAGR for 3 manually-checked companies matches hand-computed Excel value ±0.1%. Manual Excel spot check |  |
| AC-06 | ROE Accuracy | ROE for 5 companies in latest year matches companies.roe_percentage ±5% (allow for version diff). Manual comparison |  |
| AC-07 | Screener Accuracy | Quality preset screener (ROE>15, D/E<1, FCF>0) produces Screener run on full DB | ≥ 10 and ≤ 50 companies. |
| AC-08 | Dashboard Load | Company Profile screen loads for any of 92 tickers in < 3 seconds on localhost. Manual stopwatch test |  |
| AC-09 | Dashboard Export | CSV download on Screener screen produces well-formed file with correct headers. Download and open test |  |
| AC-10 | PDF Quality | No text overflow, no overlapping pages in any generated report. Visual review of 5 random tearsheets |  |
| AC-11 | API Health | GET /api/v1/health returns HTTP 200 with db_row_counts for all 10 tables. curl /api/v1/health |  |
| AC-12 | API Accuracy | GET /api/v1/companies/TCS/ratios returns rows for ≥ | 10 years. API response check |
| AC-13 | API Screener | GET /api/v1/screener?min_roe=15&max_de=1 returns consistent result with Module 3 output. Response vs Excel comparison |  |
| AC-14 | Peer Coverage | Peer percentile table populated for all 11 peer groups. All member tickers present. SELECT DISTINCT peer_group_name | → 11 |
| AC-15 | Cluster Coverage | All 92 companies assigned to a cluster (0–4). No nulls in cluster_id column. cluster_labels.csv null check |  |
| AC-16 | NLP Coverage | pros_cons_generated.csv has ≥ 1 pro and ≥ | 1 con for every company. CSV null check per company_id |
| AC-17 | Report Coverage | 92 tearsheet PDFs exist in reports/tearsheets/. Each is ≥ | 50KB. ls reports/tearsheets/ ¦ wc -l → 92 |
| AC-18 | Test Coverage | pytest count shows ≥ 60 tests collected. 0 failures. 0 errors. pytest --tb=short output |  |
| AC-19 | DQ Documentation | validation_failures.csv exists. All rows have company_id, field, issue, severity. File presence + column check |  |
| AC-20 | Documentation | analyst_guide.pdf exists and is ≥ | 10 pages. Contains screener and dashboard sections. File size and page count check |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 32

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL Standard Layout — All

19. Project Directory Structure

Code, Data, Reports & Tests

| Path | Type | Contents |
| --- | --- | --- |
| data/raw/ | Directory | 7 core Excel files (READ ONLY). Never modify. |
| data/supporting/ | Directory | 5 supplementary Excel files. |
| data/nifty100.db | SQLite | Primary database. All 10 tables. |
| src/etl/ | Directory | loader.py, validator.py, normaliser.py, schema.sql |
| src/analytics/ | Directory | ratios.py, cagr.py, cashflow_kpis.py, screener/engine.py, peer.py, clustering.py |
| src/nlp/ | Directory | parser.py (analysis.xlsx), pros_cons_generator.py |
| src/dashboard/ | Directory | app.py, pages/ (01–08), utils/charts.py, utils/db.py |
| src/api/ | Directory | main.py, routers/ (companies, screener, peers, sectors, reports, health) |
| src/reports/ | Directory | tearsheet.py, sector_report.py, portfolio_report.py, screener_report.py |
| tests/ | Directory | etl/, kpi/, api/, dq/ — 60+ pytest test files |
| config/ | Directory | screener_config.yaml, .env.template, logging_config.yaml |
| reports/tearsheets/ | Directory | 92 company tearsheet PDFs |
| reports/sector/ | Directory | 11 sector PDFs |
| reports/portfolio/ | Directory | Portfolio summary PDFs (weekly) |
| reports/radar_charts/ | Directory | 92 radar chart PNGs |
| output/ | Directory | Screener exports, ad hoc CSVs, final deliverables archive |
| notebooks/ | Directory | Exploratory Jupyter notebooks (not in production path) |
| docs/ | Directory | Project document PDF, analyst guide, openapi.json |
| requirements.txt | File | All pip dependencies pinned to minor version |
| .env | File | DB_PATH, PORT, LOG_LEVEL, SIMULATED_DATA_FLAG. Not committed to git. |
| README.md | File | Project overview, setup instructions, how to run app and API |
| Makefile | File | make load, make test, make report, make api, make dashboard |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 33

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL Financial & Technical

20. Glossary

Terms Used

Throughout This Document

| Term | Definition |
| --- | --- |
| Asset Turnover | Sales divided by total assets. Measures how efficiently a company uses its assets to generate revenue. |
| Book Value Per Share | (Equity capital + Reserves) divided by number of shares outstanding. Represents net asset value per share. |
| CAGR | Compound Annual Growth Rate. ((End Value / Start Value)^(1/n) − 1) × 100. Annualised growth metric. |
| CapEx | Capital Expenditure. Funds used to acquire or upgrade long-term physical assets. Proxy: absolute value of investing_activity. |
| Capital Allocation | How a company distributes its generated cash between reinvestment, debt repayment, and shareholder returns. |
| CFI | Cash Flow from Investing Activities. Covers CapEx, acquisitions, and investment purchases. Typically negative. |
| CFF | Cash Flow from Financing Activities. Covers debt issuance/repayment and equity transactions including dividends. |
| CFO | Cash Flow from Operations. Cash generated by core business activities. Must be positive for a healthy business. |
| CWIP | Capital Work-In-Progress. Assets under construction not yet in use. Excluded from net fixed assets. |
| D/E | Debt-to-Equity Ratio. Total borrowings divided by total equity (capital + reserves). Measures leverage. |
| Debt-Free | Company with zero or negligible borrowings. D/E = 0. ICR displayed as 'Debt Free' instead of infinity. |
| EBIT | Earnings Before Interest and Taxes. Operating_profit minus depreciation. Core operational earnings metric. |
| EBITDA | Earnings Before Interest, Taxes, Depreciation & Amortisation. Proxy: operating_profit in this dataset. |
| EPS | Earnings Per Share. Net profit divided by number of shares. Source: eps column in profitandloss table. |
| EV | Enterprise Value. Market Cap + Net Debt. Represents total company value to all capital providers. |
| EV/EBITDA | Enterprise Value divided by EBITDA. Cross-sector valuation multiple. Lower = potentially cheaper. |
| FCF | Free Cash Flow. CFO + CFI. Cash available after maintaining/expanding asset base. Core quality metric. |
| FCF Yield | FCF divided by Market Cap × 100. Higher = better value for cash-generating companies. |
| FK | Foreign Key. A database constraint linking child table rows to parent table rows via a shared key column. |
| FY | Financial Year. In India, April 1 to March 31. FY24 = April 2023 to March 2024. Labelled 'Mar-24' in source data. |
| GICS | Global Industry Classification Standard. Tiered sector taxonomy: Sector → Industry Group → Industry → |
| ICR | Interest Coverage Ratio. (EBIT + Other Income) / Interest expense. Measures ability to service debt. |
| KPI | Key Performance Indicator. A quantifiable measure used to evaluate business performance. 50+ defined in Section 13. |
| Large Cap | Companies with market capitalisation > ■20,000 Crore. All Nifty 100 companies qualify. |
| Nifty 100 | NSE India index of 100 largest companies by free-float market cap. This dataset covers 92 of those companies. |
| NPM | Net Profit Margin. Net profit divided by total sales × 100. Expressed as percentage. |
| NBFC | Non-Banking Financial Company. Lender/financial services firm that is NOT a bank. High D/E structurally normal. |
| NSE | National Stock Exchange of India. Primary stock exchange. Ticker symbols used as company primary keys. |
| OPM | Operating Profit Margin. Operating profit divided by sales × 100. EBITDA margin proxy. |
| P/B | Price-to-Book Ratio. Market Cap divided by Book Value (equity + reserves). >1 means market premium to assets. |
| P/E | Price-to-Earnings Ratio. Market Cap divided by Net Profit. Standard equity valuation multiple. |
| PAT | Profit After Tax. Same as Net Profit in this dataset. |
| PBT | Profit Before Tax. Net Profit divided by (1 − tax_percentage/100). Pre-tax earnings. |
| ROCE | Return on Capital Employed. EBIT / (Equity + Borrowings) × 100. Measures returns on all capital, not just equity. |
| ROE | Return on Equity. Net Profit / (Equity + Reserves) × 100. Measures returns on shareholders' funds. |
| SQLite | Serverless, file-based relational database. Single .db file. Zero configuration. Used for this project's data store. |

Sub-Industry.

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 34

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

| Term | Definition |
| --- | --- |
| Turnaround Flag | Applied to CAGR calculations where the base year value is negative and end year value is positive. CAGR set to None. |
| UW | Usable Width. PDF page width (21 cm) minus margins (3 cm) = 16.6 cm. All table column widths must sum to UW. |
| Winsorisation | Statistical technique: cap extreme values at P10/P90. Prevents outliers from distorting composite score normalisation. |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 35

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

From Clone to

21. Environment Setup & Quick-Start Guide

Running App in Under

30 Minutes

| Step | Command / Action | Expected Output |
| --- | --- | --- |
| 1. Clone / unzip project | unzip nifty100_project.zip -d nifty100/ | Project directory created with data/, src/, tests/, config/ |
|  | 2. Create virtual environment python3 -m venv .venv && source .venv/bin/activate (.venv) prompt in terminal |  |
| 3. Install dependencies | pip install -r requirements.txt | All 20 libraries installed; no errors |
|  | 4. Configure environmentcp config/.env.template .env && nano .env | Set DB_PATH=data/nifty100.db; PORT=8000; LOG_LEVEL=INFO |
| 5. Build database (ETL) | python src/etl/loader.py (or: make load) | nifty100.db created; load_audit.csv shows 12 files loaded |
| 6. Run KPI computation |  | python src/analytics/ratios.py (or: make ratios) financial_ratios table populated; 1,100+ rows |
| 7. Run test suite | pytest tests/ --html=reports/pytest_report.html (or: make test) 60+ tests collected; 0 failures |  |
|  | 8. Generate PDF reports python src/reports/portfolio_report.py (or: make report) reports/tearsheets/ populated with 92 PDFs |  |
|  | 9. Start Streamlit dashboardstreamlit run src/dashboard/app.py (or: make dashboard) Browser opens at http://localhost:8501 |  |
| 10. Start REST API | uvicorn src.api.main:app --port 8000 (or: make api) API running at http://localhost:8000/docs |  |

| Makefile Target | What it does | When to use |
| --- | --- | --- |
| make load | Runs ETL: loads all 12 files into nifty100.db. Re-runnable (idempotent). | Day 1 and after any source file update |
| make ratios | Runs Ratio Engine: populates financial_ratios table. | After make load. Re-run after any KPI formula change. |
| make test | Runs full pytest suite. Generates HTML report. | Before every commit. Must be 0 failures. |
| make report | Generates all PDF reports: 92 tearsheets + 11 sector + 1 portfolio. | Sprint 5+. Run once a week for fresh reports. |
| make dashboard | Starts Streamlit on port 8501. | Day-to-day analytics work. |
| make api | Starts FastAPI/Uvicorn on port 8000. | Sprint 6+. When dashboard needs live API. |
| make clean | Deletes .pyc files, __pycache__, and test artifacts (NOT the database). Before packaging final deliverables. |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 36

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL Mandatory

22. Coding Standards & Best Practices

Conventions for All Submitted Code

| Area | Standard | Tooling / Reference |
| --- | --- | --- |
| Formatting | Black — line length 88. No manual formatting. | black src/ tests/ — run pre-commit |
| Linting | ruff — all default rules enabled. Zero linting errors before commit. | ruff check src/ tests/ |
| Type Hints | All function signatures must have type annotations. Return types mandatory. mypy (optional in S1; mandatory S4+) |  |
| Docstrings | One-line docstring for all public functions. No multi-paragraph docstrings. Example: def load_pl(path: str) -> pd.DataFrame: """Load profitandloss E |  |
| Imports | stdlib → third-party → local. One blank line between groups. ruff enforces. ruff --select I (isort-compatible) |  |
| Naming | snake_case for functions and variables. PascalCase for classes. UPPER_CASE for module-level constants. Python PEP 8 |  |
| Configuration | All thresholds in screener_config.yaml or .env. Zero hardcoded values in analytics/ or api/. python-dotenv + PyYAML |  |
| Error Handling | Wrap external I/O (file reads, URL fetches) in try/except. Log error; do not raise to user. logging module — see logging_config.yaml |  |
| Logging | Use Python logging (not print). Levels: DEBUG for ETL detail; INFO for milestones; WARNING for DQ issues; ERROR for failures. import logging; logger = logging.getLogger(__name__) |  |
| Database | Use context manager (with sqlite3.connect(DB) as conn) for all queries. Parameterised queries only — no f-string SQL. conn.execute('SELECT * FROM t WHERE id = ?', (ticker,)) |  |
| Testing | One test file per source module. Test file: tests/etl/test_loader.py mirrors src/etl/loader.py. pytest conventions — fixtures in conftest.py |  |
| Git | Commit message format: [S1] feat: load P&L from Excel — sprint tag + type + description. Max 72 chars. No squash commits. Each commit must be a coherent unit. |  |

23. ETL Edge Cases — Complete Reference

| Source Field | Raw Value | normalize_year() Output | Action |
| --- | --- | --- | --- |
| year | Mar-23 | 2023-03 | Standard format — most common |
| year | Mar 23 | 2023-03 | Strip space before parse |
| year | March-2023 | 2023-03 | Full month name support |
| year | 2023 | 2023-03 | Integer year → assume March FY close |
| year | FY23 | 2023-03 | FY prefix removal |
| year | Dec-22 | 2022-12 | December year-end company (e.g. NESTLEIND) |
| year | Jun-23 | 2023-06 | June year-end (some banks) |
| year | 2023-03 | 2023-03 | Already normalised — pass through |
| year | garbage | PARSE_ERROR | Reject row; log raw value to parse_failures.csv |
| company_id | TCS | TCS | Strip whitespace both sides |
| company_id | tcs | TCS | Upper-case |
| company_id | BAJAJ-AUTO | BAJAJ-AUTO | Hyphen preserved — valid NSE ticker |
| company_id | M&M | M&M | Ampersand preserved — valid NSE ticker |
| company_id |  | MISSING | Reject row — no FK match possible |

23.1 CAGR Edge Case Decision Table

| Base Year Value | End Year Value | CAGR Result | Flag | Display As |
| --- | --- | --- | --- | --- |
| Positive (> 0) | Positive (> 0) | Computed normally | — | e.g. 18.3% |
| Positive (> 0) | Negative (< 0) | None | DECLINE_TO_LOSS | N/A — turned loss |
| Negative (< 0) | Positive (> 0) | None | TURNAROUND | Turnaround ↑ |
| Negative (< 0) | Negative (< 0) | None | BOTH_NEGATIVE | N/A — both loss |
| Zero | Any | None | ZERO_BASE | N/A — base=0 |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 37

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

| Base Year Value | End Year Value | CAGR Result | Flag | Display As |
| --- | --- | --- | --- | --- |
| < 3yr history | Any | None | INSUFFICIENT | N/A — < 3yr |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 38

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

Ready-to-Run Queries

24. Sample SQL Queries

for Common Analytical

Tasks

| Query Name | SQL | Purpose |
| --- | --- | --- |
|  | Top 10 ROE Companies (Latest Year) SELECT r.company_id, c.company_name, r.return_on_equity_pct FROM financial_ratios r JOIN companies c ON r.company_id=c.id WHERE rIdentify highest ROE companies for quality screener |  |
| Debt-Free Companies | SELECT company_id, year, debt_to_equity FROM financial_ratios WHERE debt_to_equity = 0 AND year=(SELECT MAX(year) FROM financiFilter zero-debt companies for debt-free screener |  |
|  | Consecutive FCF Positive (5yr) SELECT company_id, COUNT(*) AS positive_fcf_yrs FROM financial_ratios WHERE free_cash_flow_cr > 0 GROUP BY company_id HAVINGIdentify consistently cash-generating companies |  |
| Sector Median ROE | SELECT s.broad_sector, ROUND(AVG(r.return_on_equity_pct),1) AS median_roe FROM financial_ratios r JOIN sectors s ON r.company_id=sSector-level profitability comparison |  |
|  | Capital Allocation Pattern CountSELECT pattern_label, COUNT(*) AS companies FROM capital_allocation WHERE year=(SELECT MAX(year) FROM capital_allocation) GRODistribution of capital allocation patterns across Nifty 100 |  |
| Revenue CAGR > 15% (5yr) | SELECT r.company_id, c.company_name, r.revenue_cagr_5yr FROM financial_ratios r JOIN companies c ON r.company_id=c.id WHERE r.reHigh-growth revenue screener |  |
| Missing Annual Reports | SELECT c.id, c.company_name, 2024-COUNT(d.Year) AS missing_yrs FROM companies c LEFT JOIN documents d ON c.id=d.company_id Identify companies with documentation gaps |  |
| Peer Group Rankings (ROE) | SELECT p.peer_group_name, r.company_id, r.return_on_equity_pct, RANK() OVER (PARTITION BY p.peer_group_name ORDER BY r.returnIntra-peer ROE ranking for all 11 peer groups |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 39

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL screener_config.yaml

25. Screener Configuration Reference

— All Threshold Definitions

| Preset Name | Filters Applied | Ranking Metric | Expected Company Count |
| --- | --- | --- | --- |
| Quality Compounder | ROE > 15%, D/E < 1.0, FCF > 0, Revenue CAGR 5yr > 10%Composite Score (desc) 15–35 companies |  |  |
| Value Pick | P/E < 20, P/B < 3.0, D/E < 2.0, Dividend Yield > 1% | FCF Yield (desc) | 10–25 companies |
| Growth Accelerator | PAT CAGR 5yr > 20%, Revenue CAGR 5yr > 15%, D/E < 2.0PAT CAGR 5yr (desc) |  | 8–20 companies |
| Dividend Champion | Dividend Yield > 2%, Dividend Payout < 80%, FCF > 0 | Dividend Yield (desc) | 10–20 companies |
| Debt-Free Blue Chip | D/E = 0, ROE > 12%, Revenue > 5,000 Cr | ROE (desc) | 15–30 companies |
| Turnaround Watch | Revenue CAGR 3yr > 10%, FCF improving (positive latest yr), D/E declining Revenue CAGR 3yr (desc)5–15 companies |  |  |

25.1 Composite Score Weights

| Dimension | Weight | Inputs | Normalisation |
| --- | --- | --- | --- |
| Profitability | 35% | ROE (15%), ROCE (10%), NPM (10%) | Winsorise P10–P90; scale 0–100 per metric; weighted avg |
| Cash Quality | 30% | FCF CAGR 5yr (15%), CFO/PAT ratio (10%), FCF > 0 flag (5%) Same; FCF flag = 100 if positive, 0 if negative |  |
| Growth | 20% | Revenue CAGR 5yr (10%), PAT CAGR 5yr (10%) Same; CAGR flags (Turnaround) | → score = 0 |
| Leverage | 15% | D/E score (10%), ICR score (5%) | D/E: 0=100, 0.5=85, 1=70, 2=50, >5=0. ICR: >10=100, 5=75, 3=50, <1.5=0 |

26. Dashboard Screen Specifications

| Screen | URL Path | Key Data Queries | Interactive Elements | Export |
| --- | --- | --- | --- | --- |
| Home / Overview | / |  | SELECT from companies + financial_ratios (latest year). Sector donut data. Sector filter chips, year selector (2019–2024) — |  |
| Company Profile | /company | All tables for selected ticker. Union P&L + BS + CF. Ticker search box, year range slider |  | PDF tearsheet download link |
| Financial Screener | /screener |  | SELECT from financial_ratios + market_cap with WHERE clauses. 10 metric sliders in sidebar, preset dropdown CSV download, Excel download |  |
| Peer Comparison | /peers |  | SELECT from peer_percentiles + financial_ratios for group. Peer group dropdown, metric axis selector (8 axes) PNG chart save, Excel table |  |
| Trend Analysis | /trends |  | SELECT time-series from financial_ratios for ticker + metric. Ticker search, metric multi-select (overlay up to 3) CSV download |  |
| Sector Analysis | /sectors |  | SELECT with JOIN sectors. Bubble chart data + KPI table. Sector dropdown, year slider, metric selector for axes PNG chart save |  |
| Capital Allocation Map /capital |  | SELECT capital_allocation by year. | Year slider, click on pattern category → | company list CSV download |
| Annual Reports | /documents | SELECT from documents WHERE company_id = ticker. Ticker search, year filter |  | — |

27. Testing Framework — Test Case Reference

| Test File | Test Name | Input | Expected Output |
| --- | --- | --- | --- |
| tests/etl/test_normalise.py | test_year_mar23 | Mar-23 | 2023-03 |
| tests/etl/test_normalise.py | test_year_fy24 | FY24 | 2024-03 |
| tests/etl/test_normalise.py | test_year_dec22 | Dec-22 | 2022-12 |
| tests/etl/test_normalise.py | test_year_garbage | xyz | PARSE_ERROR |
| tests/etl/test_normalise.py | test_ticker_strip | TCS | TCS |
| tests/etl/test_normalise.py | test_ticker_lower | tcs | TCS |
| tests/kpi/test_ratios.py | test_roe_positive | net_profit=100, equity=500 | ROE = 20.0 |
| tests/kpi/test_ratios.py | test_roe_neg_equity | net_profit=100, equity=-50 | ROE = None |
| tests/kpi/test_ratios.py | test_de_debtfree | borrowings=0, equity=500 | D/E = 0 |
| tests/kpi/test_ratios.py | test_icr_debtfree | interest=0 | ICR = None (display 'Debt Free') |
| tests/kpi/test_ratios.py | test_cagr_turnaround | base=-100, end=200 | CAGR = None, flag='TURNAROUND' |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 40

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

| Test File | Test Name | Input | Expected Output |
| --- | --- | --- | --- |
| tests/kpi/test_ratios.py | test_cagr_normal | base=100, end=161, n=5 | CAGR ≈ 10.0% |
| tests/dq/test_rules.py | test_dq04_bs_balance | assets=1000, liab=1020 | DQ-04 WARNING triggered |
| tests/dq/test_rules.py | test_dq06_zero_sales | sales=0 | DQ-06 WARNING triggered |
| tests/api/test_health.py | test_health_200 | GET /api/v1/health | HTTP 200, status='ok' |
| tests/api/test_api.py | test_companies_count | GET /api/v1/companies | 92 records returned |
| tests/api/test_api.py | test_invalid_ticker | GET /api/v1/companies/INVALIDHTTP 404 |  |
| tests/api/test_api.py | test_screener_filter | GET /api/v1/screener?min_roe=15All results have ROE | ≥ 15 |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 41

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL Context for Anomaly

28. Sector Benchmarks & Expected Metric Ranges

Detection & Relative Scoring

| Sector | ROE Range | D/E Range | OPM Range | P/E Range | Notes |
| --- | --- | --- | --- | --- | --- |
| Financials (Banks) | 12–22% | > 5× (normal) | 25–45% NIM proxy | 12–25× | D/E structurally high — use NIM + ROA for banks instea |
| Financials (NBFC) | 12–20% | 3–8× (normal) | 30–55% NIM proxy | 15–30× | Higher ROA and ROE expected for consumer finance vs |
| Information Technology | 25–50% | 0–0.3× | 20–35% | 22–40× | Asset-light; high ROE; low D/E; premium P/E for growth |
| Consumer Staples (FMCG) | 20–45% | 0–0.5× | 15–28% | 40–70× | Very high P/E; brand moat; consistent margins; low debt |
| Healthcare / Pharma | 15–30% | 0–0.8× | 15–25% | 25–45× | Moderate debt; R&D adds intangible assets; premium fo |
| Energy (Oil & Gas) | 10–18% | 0.5–2× | 8–18% | 8–15× | Capital intensive; commodity-linked margins; PSU major |
| Energy (Power) | 8–15% | 1–4× | 25–40% | 12–20× | High D/E normal for regulated utilities; stable margin |
| Consumer Discretionary | 10–25% | 0.3–1.5× | 10–20% | 25–50× | Wide range; auto OEMs have lower OPM than consume |
| Materials (Steel) | 10–25% | 0.3–1× | 12–22% | 8–18× | Cyclical; margins volatile with commodity prices |
| Materials (Cement) | 12–22% | 0.3–1× | 18–28% | 18–35× | Oligopoly; regional pricing power; moderate debt |
| Industrials | 12–22% | 0.3–1.5× | 10–20% | 20–35× | Capital goods order-book driven; L&T sets benchmark |
| Conglomerates | 10–20% | 0.5–2× | 8–18% | 15–30× | Diverse revenue streams; holding company discount ap |

Usage: For relative scoring, normalise KPIs against these sector ranges rather than the universal Nifty 100 range. A D/E of 4× is a CRITICAL flag for an IT company but completely normal for a bank. The Ratio Engine uses sectors.broad_sector to select the appropriate benchmark range for each metric.

Milestone Reviews,

29. Week-by-Week Communication & Review Plan

Deliverable Handoffs & Sign-Off Schedule

| Week | Days | Review Meeting | Deliverables to Share | Go / No-Go Criteria |
| --- | --- | --- | --- | --- |
| Week 1 | D01–07 |  | End of D07 — Sprint 1 Review (30 min) nifty100.db, load_audit.csv, validation_failures.csv, exploratory_queries.sql All 10 tables loaded. Zero CRITICAL DQ failures. Cover |  |
| Week 2 | D08–14 |  | End of D14 — Sprint 2 Review (45 min) financial_ratios table (SQLite export), ratio_edge_cases.log, all KPI tests green 1,100+ rows in financial_ratios. Formula spot-checks pa |  |
| Week 3 | D15–21 |  | End of D21 — Sprint 3 Review (45 min) screener_output.xlsx (6 presets), peer_comparison.xlsx (11 groups), radar chart samples 6 screeners operational. 11 peer groups populated. All |  |
| Week 4 | D22–28 |  | End of D28 — Sprint 4 Demo (60 min) Live Streamlit dashboard demo, valuation_summary.xlsx All 8 screens load without errors. Screener returns corre |  |
| Week 5 | D29–35 |  | End of D35 — Sprint 5 Review (45 min) Sample tearsheets (3 companies), pros_cons_generated.csv, cashflow_intelligence.xlsx 5 tearsheets reviewed: no overflow. NLP coverage > 90 |  |
| Week 6 | D36–42 |  | End of D42 — Sprint 6 Review (60 min) API demo (Postman), pytest_report.html, cluster_labels.csv 16 endpoints live. 60+ tests pass. Cluster labels make b |  |
| Final | D43–45 |  | D45 — Project Sign-Off (90 min) All 23 deliverables, acceptance_checklist.pdf signed All 20 acceptance gates pass. Lead signs acceptance_c |  |

29.1 Daily Stand-Up Format (5 minutes per person)

| Question | Guidance | Max Time |
| --- | --- | --- |
| What did I complete yesterday? | Name the specific deliverable or sub-task completed. Reference the sprint task board item. 90 seconds |  |
| What will I complete today? | Commit to a specific deliverable — not vague ('work on module X'). Name the file/function. 90 seconds |  |
| What is blocking me? | Only blockers that cannot self-resolve within 2 hours. Escalate to team lead after 2 hours. 60 seconds |  |
| Anything to share? | Optional: share a finding, risk spotted, or cross-team dependency discovered. Keep it brief. 60 seconds |  |

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 42

NIFTY 100 FINANCIAL INTELLIGENCE PLATFORM PROJECT EXECUTION PLAN v1.0 · CONFIDENTIAL

Appendix A — Dataset File Checksums & Version Control

File Integrity

Reference for Source Data

| File | Size (approx) | Rows | SHA-256 (run at project start) | Notes |
| --- | --- | --- | --- | --- |
| companies.xlsx | ~50 KB | 92 | Run: sha256sum data/raw/companies.xlsx | Core reference — never modify |
| profitandloss.xlsx | ~180 KB | 1,276 | Run: sha256sum data/raw/profitandloss.xlsx | Core time-series — never modify |
| balancesheet.xlsx | ~190 KB | 1,312 | Run: sha256sum data/raw/balancesheet.xlsx Core time-series — never modify |  |
| cashflow.xlsx | ~130 KB | 1,187 | Run: sha256sum data/raw/cashflow.xlsx | Core time-series — never modify |
| analysis.xlsx | ~20 KB | 20 | Run: sha256sum data/raw/analysis.xlsx | Partial coverage — never modify |
| documents.xlsx | ~200 KB | 1,585 | Run: sha256sum data/raw/documents.xlsx | URL repository — never modify |
| prosandcons.xlsx | ~15 KB | 16 | Run: sha256sum data/raw/prosandcons.xlsx | Partial coverage — never modify |
| sectors.xlsx | ~20 KB | 92 | Run: sha256sum data/supporting/sectors.xlsx Created — update if sector changes |  |
| stock_prices.xlsx | ~400 KB | 5,520 | Run: sha256sum data/supporting/stock_prices.xlsx Simulated — label in dashboard |  |
| market_cap.xlsx | ~60 KB | 552 | Run: sha256sum data/supporting/market_cap.xlsx Simulated — label in dashboard |  |
| financial_ratios.xlsx | ~160 KB | 1,184 | Run: sha256sum data/supporting/financial_ratios.xlsx Computed — regenerate from DB |  |
| peer_groups.xlsx | ~15 KB | 56 | Run: sha256sum data/supporting/peer_groups.xlsx Created — update if groups change |  |

Appendix B — Contact & Escalation Matrix

| Role | Responsibility | Response SLA | Escalation Path |
| --- | --- | --- | --- |
|  | Team Lead / Project ManagerSprint planning, risk decisions, final sign-off on all deliverables Same day |  | — |
| Data Engineer | ETL module (Module 1), database schema, DQ rules, pipeline reliability 4 hours for CRITICAL DQ failures Escalate to Team Lead after 2hr block |  |  |
| Analytics Engineer | Ratio Engine (Module 2), Screener (Module 3), Peer Engine (Module 4) Same sprint day Escalate to Team Lead for business logic decisions |  |  |
| Dashboard Developer | Streamlit app (Module 5), chart design, UX | Same sprint day | Escalate for data availability issues → |
| API Developer | FastAPI server (Module 11), OpenAPI docs, Postman collection Same sprint day |  | Escalate for DB access issues → |
| QA / Testing | Test suite (Module 12), acceptance criteria verification, sign-off checklist 24hr for test failures Escalate to Team Lead for acceptance gate failures |  |  |

Data Engineer

Data Engineer

Document Sign-Off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager / Team Lead |  | _________________________ | _____________ |
| Data Engineering Lead |  | _________________________ | _____________ |
| Analytics Lead |  | _________________________ | _____________ |
| QA Lead |  | _________________________ | _____________ |

This document is CONFIDENTIAL and intended solely for the internal project team. No part of this document may be reproduced or shared externally without written approval from the Project Manager. Version 1.0 | Prepared for: Data Analytics Platform Initiative | 45-Day Execution Plan | All monetary figures in ■ Crore unless otherwise stated.

DATA ANALYTICS DIVISION · INTERNAL USE ONLY Page 43